CE-018 PROJECT CONTROLS ASSURANCE REPORT

NEC4 Decision-Readiness Assessment — Scenario S1 — Rev 3.0

| Project | Westbridge Station Access and Enabling Works (WSAE) |
| --- | --- |
| Client | Westbridge Transit Authority |
| Contractor | Northstar Civil Engineering Ltd |
| Interface organisation | CityRail Operations |
| Event | CE-018 — Restricted access to the Platform 4 worksite |
| Related early warning | EW-006 — separate earlier warning concerning the same access issue |
| Contract scenario | S1 — NEC4 ECC demonstration |
| Report ID / revision | CE018-S1-NEC4-DR-R3.0 / Rev 3.0 |
| Evidence cut-off | 2026-03-31 |
| Prepared for | Elena Brooks, NEC4 Project Manager |
| Prepared by | CE-018 Project Controls Assurance Assistant (non-contractual support) |
| Decision owner | Elena Brooks — NEC4 Project Manager |
| Control owner | Sofia Khan — Project Controls Lead |
| Report status | ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED |
| Classification | Fictional Demonstration Data |

FICTIONAL DEMONSTRATION DATA Not a contractual assessment or communication. Elena Brooks, NEC4 Project Manager, retains the contractual decision on CE-018.

EXECUTIVE DECISION BRIEF

Recommended route: READY WITH CONDITIONS. All four assurance tests score 2 (Pass) except T3 Configured NEC4 route and clock, which scores 1 (bounded limitation) — no critical failure is present. Schedule effect evidenced: 10 working days; commercial exposure evidenced: GBP 185,000, consistent across Quotation Rev B, Cost Forecast P07, Risk Register RISK-044 and Change Register CHG-018. Pending decision: Elena Brooks' response to Quotation Rev B, due 11 April 2026 — not overdue at the 31 March 2026 evidence cut-off. One bounded exception (EXC-01) concerns the form of programme evidence linked to the quotation and should be confirmed before that response is issued.

PROJECT AND EVENT NARRATIVE

Contractor and interface organisation:

Westbridge Station Access and Enabling Works (WSAE) required a Platform 4 worksite access window planned for 04 March 2026 under Accepted Programme AP12 (activity WSAE-A1200). On 24 February 2026 Theo Grant (CityRail Operations, Access Interface Manager) flagged an emerging operational constraint on that window. Marcus Reed (Northstar Civil Engineering Ltd, Contractor Delivery Lead) recorded early warning EW-006 on 25 February 2026 concerning the same access risk. EW-006 is a separate record from the later compensation event notification; this report does not treat EW-006 as automatically converting into CE-018.

On 04 March 2026 CityRail confirmed that only a 2-hour escorted window (03:00–05:00) was available against the planned 8-hour window, which was insufficient to establish the worksite. The Contractor notified CE-018 on 05 March 2026. Elena Brooks (NEC4 Project Manager) responded on 12 March 2026, within the configured one-week period, and requested an evidence-backed quotation. Marcus Reed submitted Quotation Rev B on 28 March 2026, within the configured three-week period, evidencing a 10 working-day schedule effect and GBP 185,000 commercial exposure. Full worksite access was achieved on 18 March 2026. Elena Brooks' response to the quotation is due 11 April 2026 and has not yet been recorded. Project Manager review is required to determine the compensation event basis, assess the quotation and issue the next contractual communication — none of which the assistant may do.

EVIDENCE AND CORRESPONDENCE REVIEWED

Correspondence:

| Record ID | Date | Sender | Recipients | Purpose / Trigger |
| --- | --- | --- | --- | --- |
| CORR-001 | 24 Feb 2026 | Theo Grant | Marcus Reed / Elena Brooks / Sofia Khan | Emerging access constraint |
| EW-006 | 25 Feb 2026 | Marcus Reed | Elena Brooks / Theo Grant / Sofia Khan | Early warning — access risk |
| ACC-004 | 04 Mar 2026 | Theo Grant | Marcus Reed / Elena Brooks / Sofia Khan | Access restriction confirmed |
| CE-018 (email) | 05 Mar 2026 | Marcus Reed | Elena Brooks / Sofia Khan | CE-018 notification |
| PMR-018 | 12 Mar 2026 | Elena Brooks | Marcus Reed / Sofia Khan | PM response / quotation request |
| QSUB-018 | 28 Mar 2026 | Marcus Reed | Elena Brooks / Sofia Khan | Quotation Rev B submission |

Programme:

| Record | Status | Data Date | Permitted Use |
| --- | --- | --- | --- |
| AP12 (PROG-AP12) | Accepted Programme | 20 Feb 2026 | What was planned when the event occurred — not to be substituted by UP13 |
| UP13 (PROG-UP13) | Current controlled update | 20 Mar 2026 | Actual progress, float and current forecast — not itself the Accepted Programme |

Commercial records:

| Record | Revision | Owner | Value |
| --- | --- | --- | --- |
| Quotation Rev B (QUOT-CE018-REVB) | B | Commercial Manager | GBP 185,000 / 10 working days |
| Cost Forecast P07 (FCST-P07) | P07 | Sofia Khan | GBP 185,000 / 10 working days |
| Risk Register (RISK-044) | 7 | Theo Grant (risk owner) | GBP 185,000 / 10 working days |
| Change Register (CHG-018) | 5 | Elena Brooks (decision owner) | GBP 185,000 / 10 working days — Not yet decided |

Control references reviewed: Source_Register.csv (SRC-001) rev 3.0; Actor_Authority_Matrix.csv (CTRL-002); Route_Clock_Rules.csv (CTRL-003); WBS_Hierarchy.csv (WBS-001); CBS_Hierarchy.csv (CBS-001); CE018_WBS_Programme_CBS_Crosswalk.csv (XWALK-001); Four_Test_Checklist.csv (CTRL-005); NEC4_Decision_Readiness_Control_Matrix.csv (CTRL-007).

ASSURANCE SCOPE AND CONTROL TESTS

| Test | Name | Why it matters |
| --- | --- | --- |
| T1 | Evidence and version | Prevents decisions using missing, superseded or unapproved records. |
| T2 | Records agree | Tests whether programme, cost, forecast, risk and change records support the same time and cost position. |
| T3 | Configured NEC4 route and clock | Tests whether the configured communication, role and response period have been followed. |
| T4 | Human authority | Prevents the assistant from taking a decision reserved to the named NEC4 role. |

PROGRAMME, COST, RISK AND CHANGE RECONCILIATION

| WBS / Activity / CBS | AP12 Position | UP13 Position | Quotation (GBP) | Forecast (GBP) | Variance |
| --- | --- | --- | --- | --- | --- |
| WSAE.20.10 / WSAE-A1200 / WSAE-C210 | Planned start/finish 04 Mar 2026 (0 days duration, milestone) | Actual finish 18 Mar 2026 — 10 working days later than AP12 | 25,000 | 25,000 | Quotation = Forecast. Risk and Change records carry the event total, not a per-CBS split. |
| WSAE.30.10 / WSAE-A1300 / WSAE-C310 | Planned 05–18 Mar 2026 (10 days) | Actual start 19 Mar 2026, in progress, early finish forecast 01 Apr 2026 — 10-day slip | 55,000 | 55,000 | Quotation = Forecast. |
| WSAE.30.10 / WSAE-A1300 / WSAE-C320 | Planned 05–18 Mar 2026 (10 days) | As above — 10-day slip | 35,000 | 35,000 | Quotation = Forecast. |
| WSAE.30.20 / WSAE-A1400 / WSAE-C510 | Planned 19–27 Mar 2026 (7 days) | Forecast start 02 Apr 2026, forecast finish 14 Apr 2026 — 10-day slip | 50,000 | 50,000 | Quotation = Forecast. |
| WSAE.10 / WSAE-M9000 / WSAE-C610 | Planned finish milestone 27 Mar 2026 | Forecast finish 14 Apr 2026 — 10-day slip | 20,000 | 20,000 | Quotation = Forecast. |
| WSAE.20.10 (event total) / / | n/a | 10 working days (matches quotation total) | 185,000 | 185,000 | All five records agree at GBP 185,000 / 10 working days. No material conflict identified. |

All five commercial records (Quotation, Forecast, Risk Register, Change Register) agree at GBP 185,000 / 10 working days. No material conflict identified; conflicting values are never averaged.

ASSURANCE FINDINGS AND SCORES

| Test | Score | Status | Finding | Consequence | Owner |
| --- | --- | --- | --- | --- | --- |
| T1 | 2 | PASS | All 11 registered Project Context files and all 12 registered S1 evidence files are present at the approved revision in Source_Register.csv, and no S2/S3/S4 replacement or conflict file is present in the evidence pack. | None — evidence base is controlled and complete for S1. | Sofia Khan |
| T2 | 2 | PASS | Quotation Rev B, Cost Forecast P07, Risk Register RISK-044 and Change Register CHG-018 all state 10 working days and GBP 185,000, and reconcile to the same WBS, activity and CBS references. UP13 variance_to_accepted_finish_working_days confirms the 10-day slip against AP12. | None — no material conflict identified in the evidence supplied. | Sofia Khan |
| T3 | 1 | BOUNDED LIMITATION | All objective route/clock dates in Route_Clock_Rules.csv are met or correctly pending-not-due (RC-EW, RC-00, RC-01, RC-02 complete; RC-03 due 11 April 2026, not overdue at the 31 March 2026 cut-off). However rule RC-02 is itself annotated ‘content still subject to NEC-05/NEC-10’: UP13 is linked to the quotation and shows the ten-working-day effect, but the evidence does not establish whether it constitutes the Clause 62.2 alterations to the Accepted Programme. This is a bounded, clearly owned limitation, not a missing record, overdue clock or unresolved Clause 64.1 trigger. | Bounded — does not block Project Manager review but should be confirmed before the RC-03 due date. | Elena Brooks (judgement) / Sofia Khan (evidence compilation) |
| T4 | 2 | PASS | Every evidence record and the requested output confirm that notification, quotation, review and decision actions sit with the named actors in Actor_Authority_Matrix.csv; the assistant has prepared cited evidence-status material only and has not notified, instructed, assessed, accepted or implemented CE-018. | None. | Sofia Khan |

Total score: 7 / 8. Critical-failure count: 0. Any score of 0 determines the route irrespective of the total score.

EXCEPTIONS, REQUIRED ACTIONS AND OWNERS

| ID | Issue | Owner | Due | Retest |
| --- | --- | --- | --- | --- |
| EXC-01 | UP13 is linked to the quotation and shows the ten-working-day effect; however, the evidence does not establish whether it constitutes the Clause 62.2 alterations to the Accepted Programme. | Elena Brooks (judgement) / Sofia Khan (evidence compilation) | 2026-04-11 (aligned to RC-03 due date) | Re-run NEC-05, NEC-10 and T3 once the Project Manager confirms the position, or by the RC-03 due date if earlier. |
| ACT-01 | Project Manager response to Quotation Rev B | Elena Brooks | 2026-04-11 | Re-run T3 and NEC-07 at or after the due date. |
| ACT-02 | Change Register CHG-018 decision — currently ‘Not yet decided’ | Elena Brooks | 2026-04-02 | Update Change Register on decision; re-run T2 cross-record reconciliation if the decision alters cost or schedule figures. |

Administrative observations (non-actionable): Early warning EW-006 was recorded one working day after the initial risk email (24→25 Feb 2026). RC-EW criticality is Major, not Critical; the basis note reserves the promptness judgement to the Project Manager. • Route_Clock_Rules.csv does not configure a distinct Clause 61.3 notification time-bar period for this demonstration. The CE-018 notification (05 Mar) followed the access restriction confirmation (04 Mar) by one day, well inside any customary period. • UP13's data date (20 Mar 2026) precedes the Quotation Rev B submission date (28 Mar 2026) by 8 days. It is the most recent controlled update in the S1 evidence pack.

DECISION ROUTE AND RETEST REQUIREMENTS

- Four-Test Result: T1=2, T2=2, T3=1, T4=2 (Total 7/8; 0 critical failures).

- Configured NEC4 Process-Assurance Result: CONFIGURED NEC4 PROCESS CONTROLS SATISFIED WITH CONDITIONS.

- Decision-Readiness Route: READY WITH CONDITIONS.

Clause 64.1 Intervention Triggers (reported separately):

- Trigger 1 — Late or missing quotation (NEC-08): NOT_TRIGGERED — Quotation submitted 28 Mar 2026, within the RC-02 due date of 02 Apr 2026.

- Trigger 2 — Incorrect assessment (NEC-09): PROJECT MANAGER JUDGEMENT — NO EVIDENCE DEFECT IDENTIFIED — cross-record reconciliation shows no unsupported or irreconcilable time/cost position in the evidence supplied.

- Trigger 3 — Programme alteration missing (NEC-10): PROJECT MANAGER JUDGEMENT — UP13 is present and linked to the quotation submission, showing the ten-working-day effect.

- Trigger 4 — Latest programme not accepted (NEC-11): NOT_TRIGGERED — AP12 is confirmed as the Accepted Programme; no non-acceptance record for a later programme submission is present.

No Clause 64.1 trigger is evidenced as definitively activated. Triggers 2 and 3 remain subject to Project Manager judgement.

NEC guidance: programme alterations must accompany a quotation where remaining work is affected, and their absence may require a Project Manager assessment. See NEC guidance on compensation-event assessments: https://www.neccontract.com/news/when-and-why-nec-project-managers-have-to-assess-compensation-events

RETAINED HUMAN AUTHORITY

The CE-018 Project Controls Assurance Assistant has extracted, linked, compared, cited and scored the registered Rev 3.0 Project Context files and the 12 S1 evidence files against the Four-Test Checklist and the NEC4 Decision-Readiness Control Matrix, and has prepared this cited assurance report, scorecard and result record. The assistant has not decided whether CE-018 is a compensation event, has not decided entitlement, has not decided that the Contractor's assessment is contractually correct, has not assessed, accepted or rejected the Quotation Rev B, and has not notified, instructed, certified, implemented or issued any contractual communication. One bounded exception (EXC-01) and two pending, not-overdue actions (ACT-01, ACT-02) remain open. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.

SOURCE REFERENCES

| Filename | Record ID | Revision | Purpose |
| --- | --- | --- | --- |
| Source_Register.csv | SRC-001 | 3.0 | Source register |
| CE018_Control_Brief.txt | CTRL-001 | 3.0 | Control brief |
| Actor_Authority_Matrix.csv | CTRL-002 | 2.1 | Authority matrix |
| Route_Clock_Rules.csv | CTRL-003 | 3.0 | Route and clock rules |
| Four_Test_Checklist.csv | CTRL-005 | 3.0 | Assurance checklist |
| Expected_Response_Structure.txt | CTRL-006 | 3.0 | Response structure |
| NEC4_Decision_Readiness_Control_Matrix.csv | CTRL-007 | 1.0 | NEC4 control matrix |
| WBS_Hierarchy.csv | WBS-001 | 1.0 | WBS |
| CBS_Hierarchy.csv | CBS-001 | 1.0 | CBS |
| CE018_WBS_Programme_CBS_Crosswalk.csv | XWALK-001 | 1.0 | Crosswalk |
| CE018_Event_Record.csv | CASE-001 | 1.1 | Event record |
| Email_01_Access_Risk_2026-02-24.eml | CORR-001 | 1.0 | Emerging operational access constraint |
| Email_02_EW006_2026-02-25.eml | EW-006 | 1.0 | Separate early-warning record concerning the same access issue |
| Email_03_Access_Restriction_2026-03-04.eml | ACC-004 | 1.0 | Planned versus actual access |
| Email_04_CE018_Notification_2026-03-05.eml | CE-018 (email) | 1.0 | Contractor notification concerning restricted access |
| Email_05_PM_Response_2026-03-12.eml | PMR-018 | 1.0 | Project Manager response and quotation request |
| Email_06_Quotation_Submission_2026-03-28.eml | QSUB-018 | 1.0 | Submission route and accompanying-record references |
| P6_Activity_Export_AP12.csv | PROG-AP12 | AP12 | What was planned at the event date |
| P6_Activity_Export_UP13.csv | PROG-UP13 | UP13 | Actual access and current forecast (required for S1) |
| CE018_Quotation_RevB.csv | QUOT-CE018-REVB | B | Quotation assessment details by WBS, activity and CBS |
| Cost_Forecast_P07.csv | FCST-P07 | P07 | Base forecast agreeing with Quotation Rev B (required for S1) |
| Risk_Register.csv | RISK-044 | 7 | Base risk record (required for S1) |
| Change_Register.csv | CHG-018 | 5 | Status, owner, next action and expected effect |