## Cover
CE018-SP-02
Uncertainty and Dependency Register
Stage 01 — Control uncertainty ¦ What is not yet known inside the approved boundary, and what the task depends on
Document reference | CE018-SP-02
Template title | Uncertainty and Dependency Register
Starter pack stage | 01 — Control uncertainty
Accountable owner | Project Controls Lead (maintains) / accountable decision owner (accepts residual uncertainty)
Version | v1.0
Status — blank template | TEMPLATE — CONFIGURE BEFORE USE
Status — worked example | ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Issue date | 2026-03-31
Project | Westbridge Station Access and Enabling Works (WSAE)
Worked example | CE-018 — Restricted access to the Platform 4 worksite
Evidence cut-off | 2026-03-31
Prepared by | CE-018 Project Controls Assurance Assistant (configured AI support, non-contractual)
Prepared for | Elena Brooks — NEC4 Project Manager
Control owner | Sofia Khan — Project Controls Lead
Classification | Fictional Demonstration Data
Previous template | CE018-SP-01 Use-Case and Controls Canvas
Next template | CE018-SP-03 Project AI Control Charter
Retained human authority
This workbook is configured Project Controls assurance support. It is not a contractual communication and it does not state NEC4 or legal compliance.
In the CE-018 worked example, Elena Brooks, NEC4 Project Manager, retains every contractual decision. In your own use, name the relevant contractual role or accountable decision owner in place of Elena Brooks.
Worksheets in this workbook
Cover — document control and retained authority
Guidance — purpose, owner, completion instructions, mandatory fields
Blank Register — reusable template
Worked Example CE-018 — completed register

## Guidance
CE018-SP-02
How to use this template
Uncertainty and Dependency Register
1. Purpose
The register records what is not yet known inside the approved boundary and what the assisted task depends on. It is completed after the Use-Case and Controls Canvas has fixed the boundary and before any evidence is assembled.
Each entry names the test or control the uncertainty would affect, so that an unresolved item can be traced to the score it will later drive. An uncertainty with no named effect is not a control item; it is background noise.
2. When to use this template
• Immediately after the canvas is approved and before evidence assembly begins.
• When a new dependency is identified during a run, including one revealed by a test failure.
• When a dependency owner changes, or a dependency date moves.
• At each retest, to confirm whether the underlying uncertainty has actually closed.
3. Accountable owner
Role | Named person in the CE-018 worked example | Responsibility for this template
Register owner | Sofia Khan — Project Controls Lead | Maintains the register, chases dependency owners and reports residual uncertainty.
Acceptor | Elena Brooks — NEC4 Project Manager | Accepts residual uncertainty at the point of decision, or declines and requires closure first.
Dependency owners | Planning Manager; Risk Manager; Commercial Manager; Marcus Reed — Contractor Delivery Lead; Theo Grant — Access Interface Manager | Own and close the dependencies raised against their records.
Configured AI support | CE-018 Assurance Assistant | Identifies and cites uncertainties. Does not close them and does not accept residual risk.
4. Completion instructions
1. Give every entry a unique ID and classify it as an uncertainty (something not yet known) or a dependency (something needed from someone else).
2. State the item factually. Do not record a conclusion where a question belongs.
3. Name the test or control the item would affect. If none is affected, question whether the item belongs in the register.
4. Record the current knowledge status: known, partly known, unknown, or in conflict.
5. Name a single owner. A dependency with no owner is not managed.
6. Give every date an explicit basis — assurance action target or configured contractual date.
7. Record how the item will be closed, and what will evidence closure.
8. Review at each retest and record whether the item actually closed, rather than assuming it did.
5. Minimum mandatory fields
Field | What it must record | Mandatory
Item ID | Unique identifier within the register. | Yes
Type | Uncertainty or Dependency. | Yes
Description | The item, stated factually. | Yes
Effect if unresolved | What the item would prevent or put at risk. | Yes
Test or control affected | The test (T1–T4) or control the item bears on. | Yes
Knowledge status | Known / partly known / unknown / in conflict. | Yes
Owner | One named owner. | Yes
Closure action and evidence | How it closes and what will evidence closure. | Yes
Date and date basis | The date and whether it is an assurance target or a configured contractual date. | Yes
Status | Open / closed / reserved to the accountable contractual role. | Yes
6. Recorded assumptions, gaps and limitations
• The register records uncertainty. It does not score evidence and carries no decision-readiness route.
• An item reserved to the accountable contractual role is not closed by assurance action; its closure is a recorded determination by that role.
• The register cannot list an unknown unknown. It is reviewed at each retest for that reason.
• Dates labelled as assurance targets are internal and are not contractual deadlines.
• Gap carried: closure is evidenced by a registered record. Where no record can evidence closure, the item stays open.
7. Relationship to the previous and next template
Position | Template | Relationship
Previous | CE018-SP-01 Use-Case and Controls Canvas | The canvas fixes the boundary; this register records what remains unknown inside it.
This template | CE018-SP-02 Uncertainty and Dependency Register | Records uncertainties and dependencies, each traced to the test or control it would affect.
Next | CE018-SP-03 Project AI Control Charter | The charter sets the standing rules that apply whatever the residual uncertainty.
8. Retained human authority
Permitted assistant support / prohibited assistant actions
Permitted: extract; link; compare; reconcile; cite; flag; score against the configured controls; identify exceptions and owners; prepare a decision-readiness pack; recommend a controlled review route.
Prohibited: decide whether CE-018 is a compensation event; decide entitlement; determine whether the Contractor's assessment is contractually correct; accept, reject or assess a quotation; issue or draft a contractual communication; determine the contractual effect of a clause; instruct or implement CE-018; claim legal or NEC4 compliance; provide legal advice.
Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018. When reused, name the relevant contractual role or accountable decision owner.

## Blank Register
CE018-SP-02
Uncertainty and Dependency Register — blank
Reusable template. One row per uncertainty or dependency.
TEMPLATE — CONFIGURE BEFORE USE
Edit the white cells only. Every entry shown as [CONFIGURE] must be set by the accountable owner before this template is used on a live task.
Row marked EXAMPLE FORMAT shows the expected format of an entry. Delete that row before use — it is not data.
This blank sheet carries no CE-018 values. Do not copy worked-example values into it.
Classification guide
Uncertainty — something the team does not yet know. Dependency — something the team needs from a named person or organisation.
Every item must name the test (T1–T4) or configured control it would affect if it stayed open. That link is what makes the register a control rather than a list.
Item ID | Type | Description | Effect if unresolved | Test / control affected | Knowledge status | Owner | Closure action and closure evidence | Date | Date basis | Status
U-01 | Uncertainty | EXAMPLE FORMAT — [CONFIGURE] state the item factually as a question, not a conclusion. | [CONFIGURE] what this would prevent | [CONFIGURE] T1 | Unknown | [CONFIGURE role] | [CONFIGURE] how it closes and what record evidences closure | [CONFIGURE] | Assurance action target — not a contractual deadline | Open
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.

## Worked Example CE-018
CE018-SP-02
Uncertainty and Dependency Register — CE-018 worked example
Compiled from the four final issued scenario records. Items U-01 to U-03 were identified before the run and were each realised in a different scenario.
COMPLETED CE-018 WORKED EXAMPLE — ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Fictional Demonstration Data. Every value is transcribed from the final issued CE-018 scenario record and is not rerun, rescored or reinterpreted here.
Source record: CE018_S1_NEC4_Decision_Readiness_Result_Rev3_0.json; CE018_S2_NEC4_Decision_Readiness_Result_Rev3_1.json; CE018_S3_NEC4_Decision_Readiness_Result_Rev3_4.json; CE018_S4_NEC4_Decision_Readiness_Result_Rev3_2.json
Read-only reference. Do not edit this sheet; copy the blank template instead.
Why three uncertainties matter more than the rest
U-01, U-02 and U-03 are the three conditions the demonstration was built to test. Each was realised in a different scenario and each produced a different decision-readiness route.
U-01 realised in S2 — mandatory evidence missing — REWORK EVIDENCE PACK. U-02 realised in S3 — records materially conflict — STOP / RECONCILE. U-03 realised in S4 — reserved action requested — REFER TO PROJECT MANAGER.
Where none of the three was realised, in S1, the route was READY WITH CONDITIONS on a bounded limitation at T3.
Item ID | Type | Description | Effect if unresolved | Test / control affected | Knowledge status | Owner | Closure action and closure evidence | Date | Date basis | Status
U-01 | Uncertainty | Will the current controlled programme update be present in the pack at the cut-off? AP12 is the Accepted Programme and must never be substituted for it. | Without it, the actual position and the programme alterations linked to the quotation cannot be evidenced. | T1, T2, T3; NEC-05, NEC-10, NEC-11 | In conflict across conditions | Planning Manager, routed by Sofia Khan | Supply the record at its approved revision and register it. Closure evidenced by the registered record in SRC-001. | 2026-04-02 | Assurance rework target — not a contractual deadline | Realised in scenario S2 — the record was absent
U-02 | Uncertainty | Do the quotation, forecast and risk records describe the same cost and time position? | Conflicting positions prevent a single reliable commercial position being put to the decision owner. | T2; NEC-09 | In conflict in scenario S3 | Sofia Khan (forecast); Risk Manager (risk); Commercial Manager via Marcus Reed (quotation) | Reconcile line by line, or record a formal variance rationale for each line. Closure evidenced by the reconciled records. | 2026-04-08 | Assurance action target — not a contractual deadline | Realised in scenario S3 — GBP 150,000 / 185,000 / 210,000
U-03 | Uncertainty | Might a reserved contractual action be requested from the assistant during the run? | A request for a reserved action is itself the configured critical condition at T4; a correct refusal does not clear the test. | T4; NEC-12 | Unknown at the outset | Elena Brooks — NEC4 Project Manager | Refuse, record the request and the refusal, and refer to the Project Manager. Closure evidenced by the recorded refusal and referral. | 2026-04-11 | Configured contractual response date (RC-03) | Realised in scenario S4 — three reserved actions requested and refused
D-01 | Dependency | CBS coding for the scenario risk record, so its cost position links to a valid CBS account under the crosswalk control. | An unlinked cost position cannot be reconciled through the crosswalk. | T1, T2 | Known — missing | Risk Manager | Apply CBS coding. Closure evidenced by the recoded record and a rerun of the crosswalk integrity check. | 2026-04-08 | Assurance action target — not a contractual deadline | Open in scenario S3 (exception E-04)
D-02 | Dependency | Registration of the CAL-5D-10H calendar definition referenced by both programme exports, including any non-working days. | Without the calendar the milestone variance cannot be resolved to a working-day figure. | T1, T2, T3 | Known — unregistered | Planning Manager | Register the calendar definition and confirm the milestone variance. Closure evidenced by the registered definition. | 2026-04-08 | Assurance action target — not a contractual deadline | Open in scenario S3 (exception E-05)
D-03 | Dependency | Explanation and evidence for the activity duration change from 7 days to 9 days between the Accepted Programme and the current update, and whether it is attributed to CE-018. | An unexplained duration change cannot be reconciled to the quotation basis. | T2 | Known — unexplained | Marcus Reed — Contractor Delivery Lead, with Planning Manager | Provide the explanation and supporting record. Closure evidenced by the registered narrative. | 2026-04-08 | Assurance action target — not a contractual deadline | Open in scenario S3 (exception E-06)
D-04 | Dependency | Calculation build-up — rates, quantities and durations — behind the five priced quotation lines. | A narrative basis without a build-up cannot be tested for internal consistency. | T1, T2 | Known — not supplied | Marcus Reed — Contractor Delivery Lead | Supply the build-up. Closure evidenced by the registered calculation record. | 2026-04-08 | Assurance action target — not a contractual deadline | Open in scenario S3 (exception E-08)
D-05 | Dependency | A recorded Project Manager acceptance or non-acceptance status for the current programme update. | Without it, the configured trigger control returns a judgement result rather than a determined one. | T1, T3; NEC-11 | Known — no record | Elena Brooks — NEC4 Project Manager | Record the submission date and the acceptance or non-acceptance status. Reserved to the Project Manager; not closed by assurance retest. | 2026-04-08 | Assurance action target — not a contractual deadline. No contractual programme-response date is calculable from the registered evidence. | Reserved to the Project Manager (exception E-07)
D-06 | Dependency | Project Manager determination of the Clause 64.1 matters reported under the configured trigger controls. | The assistant reports evidence findings only; the contractual effect is not its to determine. | T3; NEC-09, NEC-10, NEC-11 | Known — reserved | Elena Brooks — NEC4 Project Manager | Record the determination. Reserved to the Project Manager; not closed by assurance retest. | 2026-04-11 | Configured contractual response date (RC-03, Clause 62.3 / 62.6) | Reserved to the Project Manager (exception E-03)
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.