## Cover
CE018-SP-04
Approved Use-Case Register
Stage 02 — Govern AI use ¦ The controlled list of AI-assisted tasks approved against the charter
Document reference | CE018-SP-04
Template title | Approved Use-Case Register
Starter pack stage | 02 — Govern AI use
Accountable owner | Charter owner (approves) / Project Controls Lead (maintains the register)
Version | v1.0
Status — blank template | TEMPLATE — CONFIGURE BEFORE USE
Status — worked example | ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Issue date | 2026-03-31
Project | Westbridge Station Access and Enabling Works (WSAE)
Worked example | CE-018 — Restricted access to the Platform 4 worksite
Evidence cut-off | 2026-03-31
Prepared by | CE-018 Project Controls Assurance Assistant (configured AI support, non-contractual)
Prepared for | Elena Brooks — NEC4 Project Manager
Control owner | Sofia Khan — Project Controls Lead
Classification | Fictional Demonstration Data
Previous template | CE018-SP-03 Project AI Control Charter
Next template | CE018-SP-05 Data and Source Control Matrix
Retained human authority
This workbook is configured Project Controls assurance support. It is not a contractual communication and it does not state NEC4 or legal compliance.
In the CE-018 worked example, Elena Brooks, NEC4 Project Manager, retains every contractual decision. In your own use, name the relevant contractual role or accountable decision owner in place of Elena Brooks.
Worksheets in this workbook
Cover — document control and retained authority
Guidance — purpose, owner, completion instructions, mandatory fields
Blank Register — reusable template
Worked Example CE-018 — completed register

## Guidance
CE018-SP-04
How to use this template
Approved Use-Case Register
1. Purpose
The register is the controlled list of AI-assisted tasks approved on the project. A task that is not on the register is not approved, whatever its merits.
Each entry links a use case to its canvas, its approved source set, its permitted output and its accountable decision owner, so that scope creep is visible rather than gradual.
2. When to use this template
• When a new use case is proposed and has an approved canvas.
• When an approved use case changes its sources, its method, its permitted output or its decision owner.
• When a use case is suspended, retired or superseded.
• At the scheduled review of the charter.
3. Accountable owner
Role | Named person in the CE-018 worked example | Responsibility for this template
Register owner | Sofia Khan — Project Controls Lead | Maintains the register and rejects any run that has no approved entry.
Approver | Charter owner or Head of Project Controls [CONFIGURE] | Approves each use case against the charter.
Authority approver | Elena Brooks — NEC4 Project Manager | Approves the prohibited-action reference and the retained-decision entry for each use case.
Configured AI support | CE-018 Assurance Assistant | Operates only within an approved, current register entry.
4. Completion instructions
1. Give each use case a stable identifier that will not be reused if the case is retired.
2. Record the canvas reference. A use case with no approved canvas cannot be approved here.
3. Record the approved source set by register reference and revision, not by listing files.
4. Record the permitted output and the status it carries when issued.
5. Record the risk classification and what drove it — typically the reserved decisions the task sits close to.
6. Record the approval status, approver and date, and the scheduled review date.
7. Suspend the entry immediately if a control breach is recorded, and note the reason.
8. Never approve a use case that would require the assistant to take a reserved action, however it is worded.
5. Minimum mandatory fields
Field | What it must record | Mandatory
Use case ID | Stable unique identifier. | Yes
Title and description | What the task is, in one line and then in detail. | Yes
Decision supported | The single decision the output feeds. | Yes
Accountable decision owner | The named contractual role that takes the decision. | Yes
Canvas reference | The approved SP-01 canvas for this use case. | Yes
Approved source set | Register reference and revision. | Yes
Method reference | The tests and controls applied. | Yes
Permitted output and status | Artefacts permitted and the status they carry. | Yes
Prohibited-action reference | Where the reserved actions for this case are recorded. | Yes
Risk classification | The classification and what drove it. | Yes
Approval status, approver, date | Approved / suspended / retired, with approver and date. | Yes
Review date | The scheduled review date. | Yes
6. Recorded assumptions, gaps and limitations
• The register records approval of a process. It confers no contractual authority.
• An approved entry is valid only while its canvas, source set and method reference remain current.
• Risk classification is a control judgement about proximity to reserved decisions. It is not an assessment of contractual risk.
• In this demonstration the register carries a single approved use case. A live register would hold every approved AI-assisted task on the project.
• Gap carried: the register does not itself prevent an unapproved run. Platform access control does.
7. Relationship to the previous and next template
Position | Template | Relationship
Previous | CE018-SP-03 Project AI Control Charter | The charter sets the rules; the register records which specific tasks have been approved against them.
This template | CE018-SP-04 Approved Use-Case Register | Holds the controlled list of approved AI-assisted use cases and their governing references.
Next | CE018-SP-05 Data and Source Control Matrix | SP-05 fixes, record by record, the source set that each approved use case may draw on.
8. Retained human authority
Permitted assistant support / prohibited assistant actions
Permitted: extract; link; compare; reconcile; cite; flag; score against the configured controls; identify exceptions and owners; prepare a decision-readiness pack; recommend a controlled review route.
Prohibited: decide whether CE-018 is a compensation event; decide entitlement; determine whether the Contractor's assessment is contractually correct; accept, reject or assess a quotation; issue or draft a contractual communication; determine the contractual effect of a clause; instruct or implement CE-018; claim legal or NEC4 compliance; provide legal advice.
Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018. When reused, name the relevant contractual role or accountable decision owner.

## Blank Register
CE018-SP-04
Approved Use-Case Register — blank
Reusable template. One row per approved AI-assisted use case.
TEMPLATE — CONFIGURE BEFORE USE
Edit the white cells only. Every entry shown as [CONFIGURE] must be set by the accountable owner before this template is used on a live task.
Row marked EXAMPLE FORMAT shows the expected format of an entry. Delete that row before use — it is not data.
This blank sheet carries no CE-018 values. Do not copy worked-example values into it.
Approval rule
A use case may only be approved if every reserved contractual decision and communication is listed as prohibited for the assistant.
If the task cannot be described without the assistant taking a reserved action, it is not an approvable use case.
Use case ID | Title | Description | Decision supported | Accountable decision owner | Canvas ref | Approved source set | Method reference | Permitted output and status | Prohibited-action reference | Risk class | Approval status | Approver | Approval date | Review date
UC-001 | EXAMPLE FORMAT — [CONFIGURE] short title | [CONFIGURE] what the assistant does, as checkable activities | [CONFIGURE] the single decision fed | [CONFIGURE] named contractual role | SP-01 ref | [CONFIGURE] register and revision | [CONFIGURE] tests and controls | [CONFIGURE] artefacts and issued status | [CONFIGURE] where reserved actions are listed | [CONFIGURE] | Proposed | [CONFIGURE] | [CONFIGURE] | [CONFIGURE]
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.

## Worked Example CE-018
CE018-SP-04
Approved Use-Case Register — CE-018 worked example
One approved use case. The four scenarios S1 to S4 are four evidence conditions of the same use case on the same event — they are not four separate use cases and not four separate events.
COMPLETED CE-018 WORKED EXAMPLE — ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Fictional Demonstration Data. Every value is transcribed from the final issued CE-018 scenario record and is not rerun, rescored or reinterpreted here.
Source record: CE018_Control_Brief.txt (CTRL-001) Rev 3.0; Source_Register.csv (SRC-001) Rev 3.0; the four final issued scenario records
Read-only reference. Do not edit this sheet; copy the blank template instead.
One use case, four evidence conditions
S1 Rev 3.0, S2 Rev 3.1, S3 Rev 3.4 and S4 Rev 3.2 are four conditions of use case UC-001 applied to event CE-018. They must not be presented as four separate events or four separate approved use cases.
The risk classification is High because the task sits next to reserved decisions. That is precisely why the prohibited-action reference is a mandatory field.
Use case ID | Title | Description | Decision supported | Accountable decision owner | Canvas ref | Approved source set | Method reference | Permitted output and status | Prohibited-action reference | Risk class | Approval status | Approver | Approval date | Review date
UC-001 | CE-018 decision-readiness assessment | Inventory and classify registered evidence; extract dates, revisions, roles, WBS, programme activities, CBS, cost, schedule and assumptions; reconcile the Accepted Programme, current update, quotation, forecast, risk and change records; run the four assurance tests; run the twelve configured controls; report the four Clause 64.1 intervention trigger checks; prepare a cited pack, scorecard, exceptions, actions and a recommended controlled review route. | Whether the CE-018 evidence pack is ready for the Project Manager's contractual review, and which controlled review route applies. | Elena Brooks — NEC4 Project Manager | CE018-SP-01 | Source_Register.csv (SRC-001) Rev 3.0 — 11 Context records and 12 scenario evidence records | Four_Test_Checklist.csv (CTRL-005) Rev 3.0 — T1 to T4. NEC4_Decision_Readiness_Control_Matrix.csv (CTRL-007) Rev 1.0 — NEC-01 to NEC-12. | Cited assurance report; scorecard; structured result record; exception register; action and retest register; recommended route. Status: ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED. | CE018_Control_Brief.txt (CTRL-001) Rev 3.0, Prohibited Actions; Actor_Authority_Matrix.csv (CTRL-002) Rev 2.1, row AI | High — the task sits directly adjacent to reserved contractual decisions on entitlement, assessment and acceptance | Approved | Elena Brooks — NEC4 Project Manager | 2026-03-31 | 2026-04-11
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.