## Cover
CE018-SP-05
Data and Source Control Matrix
Stage 02 — Govern AI use ¦ Which records may be used, at which revision, for what purpose — and which may not
Document reference | CE018-SP-05
Template title | Data and Source Control Matrix
Starter pack stage | 02 — Govern AI use
Accountable owner | Project Controls Lead (maintains) / record owners (confirm revision and status)
Version | v1.0
Status — blank template | TEMPLATE — CONFIGURE BEFORE USE
Status — worked example | ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Issue date | 2026-03-31
Project | Westbridge Station Access and Enabling Works (WSAE)
Worked example | CE-018 — Restricted access to the Platform 4 worksite
Evidence cut-off | 2026-03-31
Prepared by | CE-018 Project Controls Assurance Assistant (configured AI support, non-contractual)
Prepared for | Elena Brooks — NEC4 Project Manager
Control owner | Sofia Khan — Project Controls Lead
Classification | Fictional Demonstration Data
Previous template | CE018-SP-04 Approved Use-Case Register
Next template | CE018-SP-06 AI Toolbox Talk Checklist
Retained human authority
This workbook is configured Project Controls assurance support. It is not a contractual communication and it does not state NEC4 or legal compliance.
In the CE-018 worked example, Elena Brooks, NEC4 Project Manager, retains every contractual decision. In your own use, name the relevant contractual role or accountable decision owner in place of Elena Brooks.
Worksheets in this workbook
Cover — document control and retained authority
Guidance — purpose, owner, completion instructions, mandatory fields
Blank Matrix — reusable template
Worked Example CE-018 — completed matrix
Excluded Assets — formatting assets that are never evidence

## Guidance
CE018-SP-05
How to use this template
Data and Source Control Matrix
1. Purpose
The matrix fixes, record by record, what the assistant may use, at which approved revision and for what purpose. It is the control that stops a superseded, unregistered or wrong-purpose record entering an assessment.
It also records what must not be used, and why. A silent exclusion is indistinguishable from an oversight, so exclusions are stated.
2. When to use this template
• Before the first run of an approved use case, and before every rerun on revised evidence.
• When a record is revised, superseded, withdrawn or replaced for a particular condition.
• When a new record type is proposed as a source.
• At every preflight inventory, to reconcile registered records against records actually present.
3. Accountable owner
Role | Named person in the CE-018 worked example | Responsibility for this template
Matrix owner | Sofia Khan — Project Controls Lead | Maintains the matrix and runs the preflight reconciliation.
Record owners | Planning Manager; Cost Manager; Risk Manager; Change Manager; Commercial Manager; Theo Grant; Marcus Reed; Elena Brooks | Confirm the approved revision and controlled status of their own records.
Approver | Elena Brooks — NEC4 Project Manager | Approves the source set for a use case that supports a contractual decision.
Configured AI support | CE-018 Assurance Assistant | Uses only registered records at approved revisions. Reports any record present but unregistered, or registered but absent.
4. Completion instructions
1. List every record with its identifier, file name, type, approved revision, version status and owner.
2. State the intended use of each record. A record used outside its stated purpose is a T1 finding, not a convenience.
3. Record the scenario or condition applicability where a record applies to some conditions and not others.
4. State the prohibited use for records that are commonly misused — above all, a current update must never be substituted for an Accepted Programme.
5. List replacement records explicitly, together with the base records they replace and the condition in which the replacement applies.
6. Record formatting and branding assets on the Excluded Assets sheet. They are never inventoried as evidence, cited, scored or added to the source register.
7. Run the preflight reconciliation before every assessment: registered count against present count, both for context records and for scenario records.
8. Where a registered record is absent, record the absence formally. Do not proceed as though the record were optional.
5. Minimum mandatory fields
Field | What it must record | Mandatory
Record ID | Unique record identifier. | Yes
File name | The controlled file name. | Yes
Record type | What kind of record it is. | Yes
Approved revision | The revision approved for use. | Yes
Version status | Current, accepted, superseded or withdrawn. | Yes
Owner | The named record owner. | Yes
Required | Whether the record is mandatory for the assessment. | Yes
Applicability | The conditions or scenarios in which the record applies. | Yes
Intended use | What the record is used for. | Yes
Prohibited use | Any use expressly not permitted. | Yes
6. Recorded assumptions, gaps and limitations
• The matrix controls source admission. It does not assess the content of any record.
• The Accepted Programme and the current programme update are separate records with separate purposes. Substituting one for the other is a prohibited use, not a shortcut.
• Replacement records apply only to the condition they are registered for. In every other condition the base record applies and the replacement is correctly absent.
• Formatting and branding assets are not evidence in any condition.
• Gap carried: the matrix records approved revisions but cannot itself detect a file whose content has changed without a revision change. That is a document-control responsibility.
7. Relationship to the previous and next template
Position | Template | Relationship
Previous | CE018-SP-04 Approved Use-Case Register | The register approves the task; the matrix fixes the records that task may draw on.
This template | CE018-SP-05 Data and Source Control Matrix | Fixes the admissible source set, record by record, with approved revisions and prohibited uses.
Next | CE018-SP-06 AI Toolbox Talk Checklist | The talk briefs the team on this source set before the run begins.
8. Retained human authority
Permitted assistant support / prohibited assistant actions
Permitted: extract; link; compare; reconcile; cite; flag; score against the configured controls; identify exceptions and owners; prepare a decision-readiness pack; recommend a controlled review route.
Prohibited: decide whether CE-018 is a compensation event; decide entitlement; determine whether the Contractor's assessment is contractually correct; accept, reject or assess a quotation; issue or draft a contractual communication; determine the contractual effect of a clause; instruct or implement CE-018; claim legal or NEC4 compliance; provide legal advice.
Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018. When reused, name the relevant contractual role or accountable decision owner.

## Blank Matrix
CE018-SP-05
Data and Source Control Matrix — blank
Reusable template. One row per registered record.
TEMPLATE — CONFIGURE BEFORE USE
Edit the white cells only. Every entry shown as [CONFIGURE] must be set by the accountable owner before this template is used on a live task.
Row marked EXAMPLE FORMAT shows the expected format of an entry. Delete that row before use — it is not data.
This blank sheet carries no CE-018 values. Do not copy worked-example values into it.
The two rules that catch most defects
A record used outside its stated intended use is a finding, not a convenience. State the intended use for every record.
Where two records describe the same subject at different points in time — an accepted baseline and a current update — record explicitly that one must never be substituted for the other.
Record ID | File name | Record type | Approved revision | Version status | Owner | Required | Applicability | Intended use | Prohibited use
[CONFIGURE] | EXAMPLE FORMAT — Controlled_File_Name.csv | [CONFIGURE] | [CONFIGURE] | Current | [CONFIGURE role] | Yes | All | [CONFIGURE] what this record is used for | [CONFIGURE] any use expressly not permitted
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.

## Worked Example CE-018
CE018-SP-05
Data and Source Control Matrix — CE-018 worked example
Transcribed from Source_Register.csv (SRC-001) Rev 3.0. Twenty-five registered records: 11 permanent Context records, 12 scenario evidence records and 2 registered S3 replacement records.
COMPLETED CE-018 WORKED EXAMPLE — ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Fictional Demonstration Data. Every value is transcribed from the final issued CE-018 scenario record and is not rerun, rescored or reinterpreted here.
Source record: Source_Register.csv (SRC-001) Rev 3.0
Read-only reference. Do not edit this sheet; copy the blank template instead.
Prohibited uses highlighted in coral
AP12 is the Accepted Programme — the controlled record of what was planned. UP13 is a current programme update carrying actuals and current forecast. Substituting UP13 for AP12 is expressly prohibited.
FCST-P07-X and RISK-044-X are registered to the S3 condition only. In S1, S2 and S4 they are correctly absent, and that absence is recorded rather than left silent.
The absence of a base record in S3 is likewise recorded: FCST-P07 and RISK-044 are marked correctly excluded, not missing.
Record ID | File name | Record type | Approved revision | Version status | Owner | Required | Applicability | Intended use | Prohibited use
SRC-001 | Source_Register.csv | Source register | 3.0 | Current | Project Controls Lead | Yes | All | Controls the approved Context and scenario evidence available to the assistant | Must not be extended with formatting or branding assets.
CTRL-001 | CE018_Control_Brief.txt | Control brief | 3.0 | Current | Project Controls Lead | Yes | All | Permitted task, assurance method, NEC4 decision-readiness gate and prohibited actions | No prohibited use recorded beyond the general rule that a record is used only for its stated purpose.
CTRL-002 | Actor_Authority_Matrix.csv | Authority matrix | 2.1 | Current | Project Controls Lead | Yes | All | Named actors, evidence responsibilities, retained authority and prohibited actions | No prohibited use recorded beyond the general rule that a record is used only for its stated purpose.
CTRL-003 | Route_Clock_Rules.csv | Configured route and clock rules | 3.0 | Current | NEC4 Project Manager | Yes | All | Clause-linked demonstration rules, periods, due dates and human authority | No prohibited use recorded beyond the general rule that a record is used only for its stated purpose.
CTRL-005 | Four_Test_Checklist.csv | Assurance checklist | 3.0 | Current | Project Controls Lead | Yes | All | Four assurance tests, scoring and mandatory decision-readiness dependencies | No prohibited use recorded beyond the general rule that a record is used only for its stated purpose.
CTRL-006 | Expected_Response_Structure.txt | Response structure | 3.0 | Current | Project Controls Lead | Yes | All | Required commercial report, scorecard, JSON and on-screen response structure | No prohibited use recorded beyond the general rule that a record is used only for its stated purpose.
CTRL-007 | NEC4_Decision_Readiness_Control_Matrix.csv | NEC4 control matrix | 1.0 | Current | NEC4 Project Manager | Yes | All | Configured procedural controls and Clause 64.1 intervention triggers | Configured process-assurance controls only. Must not be described as a legal-compliance standard.
WBS-001 | WBS_Hierarchy.csv | WBS | 1.0 | Current | Planning Manager | Yes | All | Project and work-package hierarchy | No prohibited use recorded beyond the general rule that a record is used only for its stated purpose.
CBS-001 | CBS_Hierarchy.csv | CBS | 1.0 | Current | Cost Manager | Yes | All | Cost hierarchy | No prohibited use recorded beyond the general rule that a record is used only for its stated purpose.
XWALK-001 | CE018_WBS_Programme_CBS_Crosswalk.csv | Crosswalk | 1.0 | Current | Project Controls Lead | Yes | All | Links CE-018 to WBS, programme activities and CBS | No prohibited use recorded beyond the general rule that a record is used only for its stated purpose.
CASE-001 | CE018_Event_Record.csv | Event record | 1.1 | Current | Project Controls Lead | Yes | All | Controlled CE-018 facts, status, decision owner and assessment cut-off | No prohibited use recorded beyond the general rule that a record is used only for its stated purpose.
CORR-001 | Email_01_Access_Risk_2026-02-24.eml | Email | 1.0 | Current | Theo Grant | Yes | All | Emerging operational access constraint | No prohibited use recorded beyond the general rule that a record is used only for its stated purpose.
EW-006 | Email_02_EW006_2026-02-25.eml | Early warning email | 1.0 | Current | Marcus Reed | Yes | All | Separate early-warning record concerning the same access issue | No prohibited use recorded beyond the general rule that a record is used only for its stated purpose.
ACC-004 | Email_03_Access_Restriction_2026-03-04.eml | Access confirmation | 1.0 | Current | Theo Grant | Yes | All | Planned versus actual access | No prohibited use recorded beyond the general rule that a record is used only for its stated purpose.
CE-018 | Email_04_CE018_Notification_2026-03-05.eml | CE notification email | 1.0 | Current | Marcus Reed | Yes | All | Contractor notification concerning restricted access | No prohibited use recorded beyond the general rule that a record is used only for its stated purpose.
PMR-018 | Email_05_PM_Response_2026-03-12.eml | Project Manager response | 1.0 | Current | Elena Brooks | Yes | All | Project Manager response and quotation request | No prohibited use recorded beyond the general rule that a record is used only for its stated purpose.
QSUB-018 | Email_06_Quotation_Submission_2026-03-28.eml | Quotation submission email | 1.0 | Current | Marcus Reed | Yes | All | Submission route and accompanying-record references | No prohibited use recorded beyond the general rule that a record is used only for its stated purpose.
PROG-AP12 | P6_Activity_Export_AP12.csv | Accepted Programme export | AP12 | Accepted | Planning Manager | Yes | All | What was planned at the event date | Must not be replaced by the current update UP13 when the accepted baseline position is required.
PROG-UP13 | P6_Activity_Export_UP13.csv | Current programme update | UP13 | Current controlled update | Planning Manager | Yes | S1/S3/S4 | Actual access and current forecast; deliberately omitted in S2 | Must never be substituted for the Accepted Programme AP12, and must not be treated as accepted without an acceptance record.
QUOT-CE018-REVB | CE018_Quotation_RevB.csv | Quotation | B | Current | Commercial Manager | Yes | All | Quotation assessment details by WBS, activity and CBS | Must not be assessed, accepted or rejected by the assistant.
FCST-P07 | Cost_Forecast_P07.csv | Cost forecast | P07 | Current | Project Controls Lead | Yes | S1/S2/S4 | Base forecast agreeing with Quotation Rev B | Must not be used in the S3 condition, where it is replaced by FCST-P07-X.
RISK-044 | Risk_Register.csv | Risk register | 7 | Current | Risk Manager | Yes | S1/S2/S4 | Base risk record | Must not be used in the S3 condition, where it is replaced by RISK-044-X.
CHG-018 | Change_Register.csv | Change register | 5 | Current | Change Manager | Yes | All | Status, owner, next action and expected effect | No prohibited use recorded beyond the general rule that a record is used only for its stated purpose.
FCST-P07-X | Cost_Forecast_P07_CONFLICT.csv | Scenario forecast | P07-X | Current - demonstration conflict | Project Controls Lead | Yes | S3 | S3 replacement forecast conflicting with quotation | Registered to the S3 condition only. Must not be used in S1, S2 or S4.
RISK-044-X | Risk_Register_CONFLICT.csv | Scenario risk register | 7-X | Current - demonstration conflict | Risk Manager | Yes | S3 | S3 replacement risk record conflicting with quotation and forecast | Registered to the S3 condition only. Must not be used in S1, S2 or S4.
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.

## Excluded Assets
CE018-SP-05
Excluded assets — formatting only, never evidence
These files are formatting assets. They must not be inventoried as evidence, cited, scored or added to the source register, in any condition.
Control statement
Five branding image assets support document and dashboard presentation only. They carry no project information, no revision status and no owner in the evidence sense.
Do not recreate or substitute any other organisation's logo in place of these assets.
File name | Asset type | Approved placement | Why it is excluded from the register | Registered as evidence?
Westbridge_Transit_Authority.png | Client organisation mark | Upper left of formal covers and Excel executive dashboards | A formatting asset carries no project data, no approved revision and no evidential purpose. Registering it would imply it can be cited. | No — never
CE018_Assurance_Assistant.png | Assistant identity mark | Upper right of formal covers and Excel executive dashboards | Identifies the configured support layer in the presentation. It is not a record of anything the assistant found. | No — never
CityRail_Operations.png | Interface organisation mark | Project narrative, actor or evidence sections only — not on formal covers | Illustrates which organisation an actor belongs to. The authority matrix, not the logo, is the controlled record of that. | No — never
Northstar_Civil_Engineering.png | Contractor organisation mark | Project narrative, actor or evidence sections only — not on formal covers | Illustrates the contractor in narrative sections. Contractor-issued records are registered separately and individually. | No — never
Fictional_Demonstration_Data_Badge.png | Classification badge | Beneath document control and on Excel executive dashboards | Applies the classification to the presentation. The classification itself is recorded in document control on every output. | No — never
Excluded assets are confirmed at every preflight inventory. Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.