## Cover
CE018-SP-09
Authority and Escalation Matrix
Stage 02 — Govern AI use ¦ Who evidences, who supports, who decides — and where a matter goes when it cannot be closed
Document reference | CE018-SP-09
Template title | Authority and Escalation Matrix
Starter pack stage | 02 — Govern AI use
Accountable owner | NEC4 Project Manager or equivalent accountable decision owner (approves) / Project Controls Lead (maintains)
Version | v1.0
Status — blank template | TEMPLATE — CONFIGURE BEFORE USE
Status — worked example | ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Issue date | 2026-03-31
Project | Westbridge Station Access and Enabling Works (WSAE)
Worked example | CE-018 — Restricted access to the Platform 4 worksite
Evidence cut-off | 2026-03-31
Prepared by | CE-018 Project Controls Assurance Assistant (configured AI support, non-contractual)
Prepared for | Elena Brooks — NEC4 Project Manager
Control owner | Sofia Khan — Project Controls Lead
Classification | Fictional Demonstration Data
Previous template | CE018-SP-08 Managed Assistant Instructions Template
Next template | CE018-SP-10 Evidence and Source Register
Retained human authority
This workbook is configured Project Controls assurance support. It is not a contractual communication and it does not state NEC4 or legal compliance.
In the CE-018 worked example, Elena Brooks, NEC4 Project Manager, retains every contractual decision. In your own use, name the relevant contractual role or accountable decision owner in place of Elena Brooks.
Worksheets in this workbook
Cover — document control and retained authority
Guidance — purpose, owner, completion instructions, mandatory fields
Blank Matrix — reusable template
Worked Example CE-018 — completed matrix
Escalation Routes — what goes where, and to whom

## Guidance
CE018-SP-09
How to use this template
Authority and Escalation Matrix
1. Purpose
The matrix names every actor in the assisted task, states what each is responsible for, what each supplies as evidence, and — critically — what each must not do. It is the record against which the human-authority test is scored.
The escalation routes sheet states where a matter goes when it cannot be closed at the level it was found, so that an unresolved item has a destination rather than a discussion.
2. When to use this template
• When configuring a new use case, before the assistant is given any record.
• When a role changes hands, a new role is introduced or a delegation changes.
• When a matter is escalated and the route is found to be unclear.
• At every assurance run, as the reference for the human-authority test.
3. Accountable owner
Role | Named person in the CE-018 worked example | Responsibility for this template
Matrix approver | Elena Brooks — NEC4 Project Manager | Approves the retained-authority position and every 'must not' entry.
Matrix maintainer | Sofia Khan — Project Controls Lead | Maintains the matrix and applies it when routing exceptions.
Named actors | Theo Grant; Marcus Reed; Sofia Khan; Elena Brooks; Alex Morgan | Confirm their own responsibility, evidence and prohibition entries.
Configured AI support | CE-018 Assurance Assistant | Is itself an entry in the matrix. Holds no authority and must refuse every reserved action.
4. Completion instructions
1. List every actor who supplies evidence, operates the assistant, reviews the output or takes a decision. Include the assistant itself as an entry.
2. State each actor's responsibility as an action, and the evidence that actor supplies.
3. Complete the 'must not' column for every actor, including the accountable decision owner — whose entry records that retained authority is not delegable to the assistant.
4. Record the decision question each actor answers. This is what makes the matrix usable during a run rather than only at set-up.
5. Record the journey stage so that an exception can be routed to the stage it belongs to.
6. Complete the escalation routes sheet: the trigger, the destination, the owner and whether assurance retest can close it.
7. Have the accountable contractual role approve the matrix. It is that role's authority the matrix protects.
5. Minimum mandatory fields
Field | What it must record | Mandatory
Actor ID and name | Unique identifier and named person or role. | Yes
Organisation | The organisation the actor acts for. | Yes
Role and role classification | The role and whether it is a named contractual role, an operational role, assurance support or configured AI support. | Yes
Responsibility | What the actor is responsible for doing. | Yes
Evidence supplied | The records the actor provides. | Yes
Must not | What the actor must not do. Mandatory for every actor. | Yes
Decision question | The question the actor answers during a run. | Yes
Journey stage | Where in the process the actor acts. | Yes
Escalation destination | Where a matter goes when the actor cannot close it. | Yes
6. Recorded assumptions, gaps and limitations
• The matrix records configured process roles. It does not create, vary or delegate contractual authority.
• Configured AI support is a non-contractual support layer. It holds no role under the contract and cannot receive delegated authority.
• A correct refusal by the assistant is recorded as a critical condition under the human-authority test. That is by design: the request is what is being measured, not the assistant's behaviour.
• Where an actor's 'must not' entry is blank, the matrix is incomplete and must not be approved.
• Gap carried: the matrix assumes each named role is filled and available. Where the accountable role is unavailable, the matter waits rather than moving down the list.
7. Relationship to the previous and next template
Position | Template | Relationship
Previous | CE018-SP-08 Managed Assistant Instructions Template | SP-08 configures the refusal and escalation behaviour; SP-09 names the roles that behaviour depends on.
This template | CE018-SP-09 Authority and Escalation Matrix | Names every actor, their responsibility, their prohibition and their escalation destination.
Next | CE018-SP-10 Evidence and Source Register | With roles fixed, SP-10 records the evidence those roles supply.
8. Retained human authority
Permitted assistant support / prohibited assistant actions
Permitted: extract; link; compare; reconcile; cite; flag; score against the configured controls; identify exceptions and owners; prepare a decision-readiness pack; recommend a controlled review route.
Prohibited: decide whether CE-018 is a compensation event; decide entitlement; determine whether the Contractor's assessment is contractually correct; accept, reject or assess a quotation; issue or draft a contractual communication; determine the contractual effect of a clause; instruct or implement CE-018; claim legal or NEC4 compliance; provide legal advice.
Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018. When reused, name the relevant contractual role or accountable decision owner.

## Blank Matrix
CE018-SP-09
Authority and Escalation Matrix — blank
Reusable template. One row per actor, including the configured assistant.
TEMPLATE — CONFIGURE BEFORE USE
Edit the white cells only. Every entry shown as [CONFIGURE] must be set by the accountable owner before this template is used on a live task.
Row marked EXAMPLE FORMAT shows the expected format of an entry. Delete that row before use — it is not data.
This blank sheet carries no CE-018 values. Do not copy worked-example values into it.
The 'must not' column is mandatory
Every actor has one, including the accountable decision owner, whose entry records that retained authority is not delegable to configured AI support.
A matrix with a blank 'must not' entry must not be approved.
Actor ID | Organisation | Name | Role | Role classification | Responsibility | Evidence supplied | Must not | Decision question | Journey stage | Escalation destination
[ID] | [CONFIGURE] | [CONFIGURE] | [CONFIGURE] | [CONFIGURE] | EXAMPLE FORMAT — [CONFIGURE] what this actor is responsible for doing | [CONFIGURE] records supplied | [CONFIGURE] mandatory for every actor | [CONFIGURE] the question this actor answers | [CONFIGURE] | [CONFIGURE]
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.

## Worked Example CE-018
CE018-SP-09
Authority and Escalation Matrix — CE-018 worked example
Transcribed from Actor_Authority_Matrix.csv (CTRL-002) Rev 2.1, with the escalation destination added.
COMPLETED CE-018 WORKED EXAMPLE — ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Fictional Demonstration Data. Every value is transcribed from the final issued CE-018 scenario record and is not rerun, rescored or reinterpreted here.
Source record: Actor_Authority_Matrix.csv (CTRL-002) Rev 2.1
Read-only reference. Do not edit this sheet; copy the blank template instead.
The two entries that carry the whole control
Elena Brooks must not delegate retained NEC4 authority to the assistant. The CE-018 Assurance Assistant must not notify, instruct, assess, accept or implement CE-018.
In scenario S4 those two entries were tested directly: three reserved actions were requested from the assistant, all three were refused and the matter was referred to Elena Brooks. Control NEC-12 returned FAILED_STOP_REFER and T4 scored 0.
The route became REFER TO PROJECT MANAGER on a total score of 5 of 8 — a higher total than S3, and a more restrictive route.
Actor ID | Organisation | Name | Role | Role classification | Responsibility | Evidence supplied | Must not | Decision question | Journey stage | Escalation destination
TG | CityRail Operations | Theo Grant | Access Interface Manager | Operational role | Confirm planned, requested and actual access | Access schedule; possession log; access confirmation email | Decide the NEC4 route or CE entitlement | Was access requested for the planned date, and what was actually available? | 01 Confirm the event | Sofia Khan — Project Controls Lead (record routing)
MR | Northstar Civil Engineering Ltd | Marcus Reed | Contractor Delivery Lead | Contractor business role | Evidence the effect on planned work, time and cost; notify and quote for the Contractor | Early warning; CE notification; programme narrative; quotation | Make or issue the Project Manager's decision | Does the Accepted Programme show the affected work, and what time and cost impact can we evidence? | 02 Evidence the impact | Sofia Khan — Project Controls Lead, then Elena Brooks for any contractual matter
SK | Westbridge Transit Authority | Sofia Khan | Project Controls Lead | Assurance support | Reconcile programme, cost, forecast, risk and change records; operate the assistant | Evidence register; cross-record reconciliation; exception report | Issue contractual communications or decide entitlement | Do the access, programme, quotation, forecast, risk and change records tell the same story? | 03 Reconcile the records | Elena Brooks — NEC4 Project Manager
EB | Westbridge Transit Authority | Elena Brooks | NEC4 Project Manager | Named NEC4 role | Select the contractual route and make the retained human decision | Project Manager communications; decision and action log | Delegate retained NEC4 authority to the assistant | Is the evidence sufficient, and which NEC4 communication or decision is now required? | 04 Make the NEC4 decision | Retained — the decision stops here. No onward escalation within the configured process.
AM | Westbridge Transit Authority | Alex Morgan | NEC4 Supervisor | Separate named NEC4 role | Provide inspection or defect evidence where relevant | Inspection records | Make the Project Manager's CE decision | Is there relevant inspection evidence that changes the factual record? | Secondary evidence source | Elena Brooks — NEC4 Project Manager
AI | Managed assurance workspace | CE-018 Assurance Assistant | Configured AI support | Non-contractual support | Extract, link, compare, cite, flag and prepare | Cited evidence-status and exception report | Notify, instruct, assess, accept or implement CE-018 | What can be evidenced, what conflicts, and who must act next? | Support layer | Sofia Khan — Project Controls Lead; any reserved matter goes directly to Elena Brooks
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.

## Escalation Routes
CE018-SP-09
Escalation routes
What triggers an escalation, where it goes, who owns it and whether assurance retest can close it.
Trigger | What it means | Destination | Owner | Closed by assurance retest?
Required evidence missing | A record registered as required is not present at the cut-off. The gap is not offset by other records reconciling. | Rework the evidence pack | Record owner, routed by Sofia Khan | Yes — once the record is registered and supplied
Records conflict materially | Two or more registered records describe different cost or time positions for the same event. | Stop and reconcile | Record owners, routed by Sofia Khan | Yes — once reconciled or a formal variance rationale is recorded
Route or clock potentially breached | A configured communication route or response period may not have been met. | Refer to the Project Manager | Elena Brooks — NEC4 Project Manager | No — the contractual effect is determined by the Project Manager
Clause 64.1 trigger matter reported | An objective trigger check returns a result reserved to Project Manager judgement. | Refer to the Project Manager | Elena Brooks — NEC4 Project Manager | No — determination is recorded by the Project Manager
Required programme alteration absent | The quotation pack does not carry the programme or alteration the configured content check requires. | Rework, or refer for Project Manager assessment | Marcus Reed, with Elena Brooks | Partly — presence is retestable; acceptability is not
Authority unclear | It is not clear which role is entitled to take the next action. | Refer to the Project Manager | Elena Brooks — NEC4 Project Manager | No
Reserved action requested from the assistant | A contractual decision or communication reserved to a named role is requested from configured AI support. | Refuse, record and refer to the Project Manager | Elena Brooks — NEC4 Project Manager | No — and a correct refusal does not clear the human-authority test
Evidence-quality defect with a named owner | A bounded defect such as missing coding, an unregistered definition or an unexplained change. | Action register, with owner and date | The named record owner | Yes — on closure of the action and rerun of the affected tests
Date basis applies to every escalation
Every escalation carries a date and an explicit basis. An assurance action target is an internal rework date; a configured contractual date arises under the configured process.
In the CE-018 runs the assurance targets sit at 2026-04-02 and 2026-04-08; the configured contractual response date RC-03 is 2026-04-11. The two must never be presented as the same kind of date.
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.