## Cover
CE018-SP-10
Evidence and Source Register
Stage 03 — Test the output ¦ What was actually supplied, at what revision, and what was registered but absent
Document reference | CE018-SP-10
Template title | Evidence and Source Register
Starter pack stage | 03 — Test the output
Accountable owner | Project Controls Lead (compiles) / record owners (confirm revision and status)
Version | v1.0
Status — blank template | TEMPLATE — CONFIGURE BEFORE USE
Status — worked example | ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Issue date | 2026-03-31
Project | Westbridge Station Access and Enabling Works (WSAE)
Worked example | CE-018 — Restricted access to the Platform 4 worksite
Evidence cut-off | 2026-03-31
Prepared by | CE-018 Project Controls Assurance Assistant (configured AI support, non-contractual)
Prepared for | Elena Brooks — NEC4 Project Manager
Control owner | Sofia Khan — Project Controls Lead
Classification | Fictional Demonstration Data
Previous template | CE018-SP-09 Authority and Escalation Matrix
Next template | CE018-SP-11 Four-Test Assurance Checklist
Retained human authority
This workbook is configured Project Controls assurance support. It is not a contractual communication and it does not state NEC4 or legal compliance.
In the CE-018 worked example, Elena Brooks, NEC4 Project Manager, retains every contractual decision. In your own use, name the relevant contractual role or accountable decision owner in place of Elena Brooks.
Worksheets in this workbook
Cover — document control and retained authority
Guidance — purpose, owner, completion instructions, mandatory fields
Blank Register — reusable template
Preflight Reconciliation — registered against present, by condition
Worked Example CE-018 — the S3 evidence inventory

## Guidance
CE018-SP-10
How to use this template
Evidence and Source Register
1. Purpose
The register records what was actually supplied for a specific assessment run: every record present, its revision, its owner, its intended use and its locator. It is the evidence base the four tests are scored against.
Its most important function is the preflight reconciliation: registered count against present count. A registered record that is absent must be recorded as absent, not quietly omitted.
2. When to use this template
• At the start of every assessment run, before any test is scored.
• After rework, to confirm that the previously absent record is now present at its approved revision.
• When a scenario or condition uses replacement records in place of base records.
• Whenever a record is supplied that is not in the source control matrix.
3. Accountable owner
Role | Named person in the CE-018 worked example | Responsibility for this template
Register compiler | Sofia Khan — Project Controls Lead | Compiles the register and runs the preflight reconciliation.
Record owners | Planning Manager; Cost Manager; Risk Manager; Change Manager; Commercial Manager; Theo Grant; Marcus Reed; Elena Brooks | Confirm the revision and controlled status of their own records.
Reviewer | Elena Brooks — NEC4 Project Manager | Receives the register with the assurance pack and sees exactly what the assessment rested on.
Configured AI support | CE-018 Assurance Assistant | Inventories, classifies and cites. Does not supply, approve or substitute a record.
4. Completion instructions
1. Reconcile the count first: registered context records against present, and registered scenario records against present. Record both counts even when they match.
2. List every record present, with its identifier, file name, type, revision and status, owner, intended use and locator.
3. Record every registered record that is absent, with the reason, if known, and the consequence.
4. Record every record correctly excluded for the condition being run, and state why it is excluded. An exclusion that is not stated reads as an omission.
5. Record any record present but unregistered. It is not evidence until it is registered.
6. Confirm that no formatting or branding asset appears anywhere in the register.
7. Do not proceed to scoring until the reconciliation is complete and every discrepancy is recorded.
5. Minimum mandatory fields
Field | What it must record | Mandatory
Record ID | Unique record identifier. | Yes
File name | The file as supplied. | Yes
Record type | What kind of record it is. | Yes
Revision and status | The revision supplied and its controlled status. | Yes
Owner | The named record owner. | Yes
Required | Whether the record is mandatory for this run. | Yes
Present | Present, absent or correctly excluded. | Yes
Intended use | What the record is used for in this assessment. | Yes
Locator | Where in the record the cited values sit. | Yes
Preflight reconciliation | Registered count against present count, for context and scenario records. | Yes
6. Recorded assumptions, gaps and limitations
• The register records what was supplied. It does not assess whether the content is correct — that is the four tests.
• A record is evidence only if it is registered. A helpful but unregistered file is recorded as unregistered and is not cited.
• A replacement record applies only to the condition it is registered for; in every other condition the base record applies and the replacement is correctly absent.
• Formatting and branding assets never appear in the register, in any condition.
• Gap carried: the register cannot detect a record whose content changed without a revision change.
7. Relationship to the previous and next template
Position | Template | Relationship
Previous | CE018-SP-09 Authority and Escalation Matrix | SP-09 names who supplies what; SP-10 records what they actually supplied.
This template | CE018-SP-10 Evidence and Source Register | Records the evidence base for one assessment run and reconciles it against the registered set.
Next | CE018-SP-11 Four-Test Assurance Checklist | The four tests are scored against this register.
8. Retained human authority
Permitted assistant support / prohibited assistant actions
Permitted: extract; link; compare; reconcile; cite; flag; score against the configured controls; identify exceptions and owners; prepare a decision-readiness pack; recommend a controlled review route.
Prohibited: decide whether CE-018 is a compensation event; decide entitlement; determine whether the Contractor's assessment is contractually correct; accept, reject or assess a quotation; issue or draft a contractual communication; determine the contractual effect of a clause; instruct or implement CE-018; claim legal or NEC4 compliance; provide legal advice.
Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018. When reused, name the relevant contractual role or accountable decision owner.

## Blank Register
CE018-SP-10
Evidence and Source Register — blank
Reusable template. One row per record. Use the Present column to record 'Present', 'ABSENT — registered but not supplied' or 'Correctly excluded for this condition'.
TEMPLATE — CONFIGURE BEFORE USE
Edit the white cells only. Every entry shown as [CONFIGURE] must be set by the accountable owner before this template is used on a live task.
Row marked EXAMPLE FORMAT shows the expected format of an entry. Delete that row before use — it is not data.
This blank sheet carries no CE-018 values. Do not copy worked-example values into it.
Three states, not two
Present — supplied at the approved revision. ABSENT — registered as required but not supplied; this is a finding. Correctly excluded — registered to another condition and rightly not here; this is not a finding.
Recording the third state explicitly is what stops a correct exclusion being read as a missing record, and a missing record being read as an intentional exclusion.
Record ID | File name | Record type | Revision / status | Owner | Required | Present | Intended use in this assessment | Locator
[ID] | EXAMPLE FORMAT — Controlled_File_Name.csv | [CONFIGURE] | [rev] / Current | [CONFIGURE role] | Yes | Present | [CONFIGURE] what it is used for here | [CONFIGURE] row, field or message reference
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.

## Preflight Reconciliation
CE018-SP-10
Preflight reconciliation — registered against present
Run before any test is scored. The counts below are transcribed from each condition's own issued record.
COMPLETED CE-018 WORKED EXAMPLE — ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Fictional Demonstration Data. Every value is transcribed from the final issued CE-018 scenario record and is not rerun, rescored or reinterpreted here.
Source record: the four final issued CE-018 scenario records
Read-only reference. Do not edit this sheet; copy the blank template instead.
Condition | Evidence condition | Context registered | Context present | Scenario registered | Scenario present | Reconciles? | What the reconciliation showed
S1 Rev 3.0 | Evidence complete; one bounded limitation remains | 11 | 11 | 12 | 12 | Yes | Preflight passed and the assessment proceeded. No conflict files present.
S2 Rev 3.1 | Mandatory evidence missing | 11 | 11 | 12 | 11 | No — one scenario record absent | One registered scenario record was not supplied. The absence was recorded formally and drove critical failures at T1, T2 and T3.
S3 Rev 3.4 | Records materially conflict | 11 | 11 | 12 | 12 | Yes | All 23 registered records present. Two registered replacement records in use; the two base records they replace recorded as correctly excluded.
S4 Rev 3.2 | A reserved contractual action was requested | 11 | 11 | 12 | 12 | Yes | All 23 registered records present. The condition tested at S4 concerns authority, not evidence completeness.
Why the count matters more than it looks
In S2 the difference between 12 registered and 11 present is a single record. That single absence drove three of the four tests to a score of 0 and left three of the four Clause 64.1 trigger checks unassessable.
The reconciliation is a hard gate for exactly this reason: a missing record is not offset by the fact that every record that is present reconciles perfectly.
In S3 the counts reconcile at 12 of 12 and the assessment still returned STOP / RECONCILE. A complete pack is not the same as a consistent one.
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.

## Worked Example CE-018
CE018-SP-10
Evidence and Source Register — CE-018 scenario S3 Rev 3.4
Twenty-three registered records present — 11 Context and 12 scenario — plus the two base records correctly excluded because S3 uses registered replacements.
COMPLETED CE-018 WORKED EXAMPLE — ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Fictional Demonstration Data. Every value is transcribed from the final issued CE-018 scenario record and is not rerun, rescored or reinterpreted here.
Source record: CE018_S3_NEC4_Decision_Readiness_Result_Rev3_4.json — evidence_inventory
Read-only reference. Do not edit this sheet; copy the blank template instead.
Correct exclusion is recorded, not silent
S3 uses two registered replacement records. The base forecast and base risk records they replace are registered to S1, S2 and S4 only, and are recorded here as correctly excluded rather than omitted.
The same statement appears in the other three conditions, where the replacement records are recorded as correctly absent. Neither absence is a finding.
No formatting or branding asset appears in this register. Five image assets exist in the demonstration and are excluded from the register in every condition.
Record ID | File name | Record type | Revision / status | Owner | Required | Present | Intended use in this assessment | Locator
SRC-001 | Source_Register.csv | Source register | 3.0 / Current | Project Controls Lead | Yes | Present — Context record | Controls approved Context and scenario evidence | SRC-001 row; all rows
CTRL-001 | CE018_Control_Brief.txt | Control brief | 3.0 / Current | Project Controls Lead | Yes | Present — Context record | Permitted task, method, prohibited actions | Rev 3.0 header; Permitted/Prohibited sections
CTRL-002 | Actor_Authority_Matrix.csv | Authority matrix | 2.1 / Current | Project Controls Lead | Yes | Present — Context record | Named actors and retained authority | Rows TG, MR, SK, EB, AM, AI
CTRL-003 | Route_Clock_Rules.csv | Route and clock rules | 3.0 / Current | NEC4 Project Manager | Yes | Present — Context record | Configured clause periods and due dates | Rows RC-EW, RC-00, RC-01, RC-02, RC-03
CTRL-005 | Four_Test_Checklist.csv | Assurance checklist | 3.0 / Current | Project Controls Lead | Yes | Present — Context record | Four tests, scoring and dependencies | Rows T1-T4
CTRL-006 | Expected_Response_Structure.txt | Response structure | 3.0 / Current | Project Controls Lead | Yes | Present — Context record | Required report, scorecard and JSON structure | Rev 3.0 sections 1-11
CTRL-007 | NEC4_Decision_Readiness_Control_Matrix.csv | NEC4 control matrix | 1.0 / Current | NEC4 Project Manager | Yes | Present — Context record | Configured procedural controls and Clause 64.1 triggers | Rows NEC-01 to NEC-12
WBS-001 | WBS_Hierarchy.csv | WBS | 1.0 / Current | Planning Manager | Yes | Present — Context record | Work-package hierarchy | Rows WSAE, WSAE.10, WSAE.20.10, WSAE.30.10, WSAE.30.20
CBS-001 | CBS_Hierarchy.csv | CBS | 1.0 / Current | Cost Manager | Yes | Present — Context record | Cost hierarchy | Rows WSAE-C210, C310, C320, C510, C610
XWALK-001 | CE018_WBS_Programme_CBS_Crosswalk.csv | Crosswalk | 1.0 / Current | Project Controls Lead | Yes | Present — Context record | Links CE-018 to WBS, activities and CBS | All 5 rows
CASE-001 | CE018_Event_Record.csv | Event record | 1.1 / Current | Project Controls Lead | Yes | Present — Context record | Controlled CE-018 facts and cut-off | Single data row
CORR-001 | Email_01_Access_Risk_2026-02-24.eml | Email | 1.0 / Current | Theo Grant | Yes | Present — S3 scenario record | Emerging operational access constraint | Date 2026-02-24; Message-ID corr-001
EW-006 | Email_02_EW006_2026-02-25.eml | Early warning email | 1.0 / Current | Marcus Reed | Yes | Present — S3 scenario record | Separate early-warning record on the same access issue | Date 2026-02-25; Message-ID ew-006
ACC-004 | Email_03_Access_Restriction_2026-03-04.eml | Access confirmation | 1.0 / Current | Theo Grant | Yes | Present — S3 scenario record | Planned versus actual access | Date 2026-03-04; Message-ID acc-004
CE-018 | Email_04_CE018_Notification_2026-03-05.eml | CE notification email | 1.0 / Current | Marcus Reed | Yes | Present — S3 scenario record | Contractor notification of restricted access | Date 2026-03-05; Message-ID ce-018
PMR-018 | Email_05_PM_Response_2026-03-12.eml | Project Manager response | 1.0 / Current | Elena Brooks | Yes | Present — S3 scenario record | PM response and quotation request | Date 2026-03-12; Message-ID pmr-018
QSUB-018 | Email_06_Quotation_Submission_2026-03-28.eml | Quotation submission email | 1.0 / Current | Marcus Reed | Yes | Present — S3 scenario record | Submission route and accompanying-record references | Date 2026-03-28; Message-ID qsub-018
PROG-AP12 | P6_Activity_Export_AP12.csv | Accepted Programme export | AP12 / Accepted | Planning Manager | Yes | Present — S3 scenario record | What was planned at the event date | Data date 2026-02-20; rows A1100-M9000
PROG-UP13 | P6_Activity_Export_UP13.csv | Current programme update | UP13 / Current controlled update | Planning Manager | Yes | Present — S3 scenario record | Actual access and current forecast | Data date 2026-03-20; rows A1100-M9000
QUOT-CE018-REVB | CE018_Quotation_RevB.csv | Quotation | B / Current | Commercial Manager | Yes | Present — S3 scenario record | Quotation assessment details by WBS, activity and CBS | 5 rows; submitted 2026-03-28
FCST-P07-X | Cost_Forecast_P07_CONFLICT.csv | Scenario forecast (S3 replacement) | P07-X / Current - demonstration conflict | Project Controls Lead | Yes | Present — S3 scenario record | S3 replacement forecast conflicting with quotation | 5 rows; data date 2026-03-31
RISK-044-X | Risk_Register_CONFLICT.csv | Scenario risk register (S3 replacement) | 7-X / Current - demonstration conflict | Risk Manager | Yes | Present — S3 scenario record | S3 replacement risk record conflicting with quotation and forecast | Single row RISK-044-X
CHG-018 | Change_Register.csv | Change register | 5 / Current | Change Manager | Yes | Present — S3 scenario record | Status, owner, next action and expected effect | Single row CHG-018
FCST-P07 | Cost_Forecast_P07.csv | Cost forecast | P07 / registered to S1, S2 and S4 | Project Controls Lead | Yes (other conditions) | Correctly excluded for S3 | Base forecast — registered to S1/S2/S4 only; replaced in S3 by FCST-P07-X | SRC-001 row FCST-P07
RISK-044 | Risk_Register.csv | Risk register | 7 / registered to S1, S2 and S4 | Risk Manager | Yes (other conditions) | Correctly excluded for S3 | Base risk record — registered to S1/S2/S4 only; replaced in S3 by RISK-044-X | SRC-001 row RISK-044
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.