## Cover
CE018-SP-12
Test and Acceptance Scorecard
Stage 03 — Test the output ¦ Formula-driven totalling, critical-failure detection and route consistency checking
Document reference | CE018-SP-12
Template title | Test and Acceptance Scorecard
Starter pack stage | 03 — Test the output
Accountable owner | Project Controls Lead (completes) / accountable decision owner (receives)
Version | v1.0
Status — blank template | TEMPLATE — CONFIGURE BEFORE USE
Status — worked example | ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Issue date | 2026-03-31
Project | Westbridge Station Access and Enabling Works (WSAE)
Worked example | CE-018 — Restricted access to the Platform 4 worksite
Evidence cut-off | 2026-03-31
Prepared by | CE-018 Project Controls Assurance Assistant (configured AI support, non-contractual)
Prepared for | Elena Brooks — NEC4 Project Manager
Control owner | Sofia Khan — Project Controls Lead
Classification | Fictional Demonstration Data
Previous template | CE018-SP-11 Four-Test Assurance Checklist
Next template | CE018-SP-13 Configured NEC4 Decision-Readiness Control Matrix
Retained human authority
This workbook is configured Project Controls assurance support. It is not a contractual communication and it does not state NEC4 or legal compliance.
In the CE-018 worked example, Elena Brooks, NEC4 Project Manager, retains every contractual decision. In your own use, name the relevant contractual role or accountable decision owner in place of Elena Brooks.
Worksheets in this workbook
Cover — document control and retained authority
Guidance — purpose, owner, completion instructions, mandatory fields
Blank Scorecard — reusable, formula-driven
Worked Example CE-018 — four conditions reconciled by formula

## Guidance
CE018-SP-12
How to use this template
Test and Acceptance Scorecard
1. Purpose
The scorecard totals the four test scores, counts the critical failures, lists the failing test identifiers and checks that the recorded route is consistent with the critical-failure rule. Every one of those is a formula, so the sheet recalculates when a score changes.
The scorecard does not derive the route. It records the route and then tests it for consistency. That distinction is deliberate and is explained on the blank sheet.
2. When to use this template
• Immediately after the four-test checklist is scored.
• At every retest, to show the movement between runs.
• When issuing an assurance pack to the accountable decision owner.
• When reconciling a transcribed result against its source record.
3. Accountable owner
Role | Named person in the CE-018 worked example | Responsibility for this template
Scorecard owner | Sofia Khan — Project Controls Lead | Completes the score inputs and records the route and its basis.
Recipient | Elena Brooks — NEC4 Project Manager | Receives the scorecard as the summary page of the assurance pack.
Reviewer | Independent assurance reviewer [CONFIGURE] | Checks that the consistency formulas return OK before issue.
Configured AI support | CE-018 Assurance Assistant | Populates the score inputs and the citation fields. Does not set the route.
4. Completion instructions
1. Enter the four test scores in the yellow input cells. Enter 2, 1 or 0 only.
2. Read the computed total, critical-failure count and critical test identifiers. Do not type over a formula cell.
3. Enter the recorded decision-readiness route and its stated basis in the yellow input cells.
4. Check the two consistency formulas. Both must return OK before the scorecard is issued.
5. Do not attempt to compute the route from the scores. The route-priority hierarchy depends on why a test scored 0, which a score alone does not carry.
6. Where a transcribed result is being reconciled against a source record, enter the issued values separately and use the comparison formulas to confirm the transcription.
7. Record the source file name and locator for every value transcribed from an issued record.
5. Minimum mandatory fields
Field | What it must record | Mandatory
Run reference and cut-off | The run being scored and its evidence cut-off. | Yes
Four test scores | T1 to T4, each 2, 1 or 0. | Yes
Total and maximum | Computed by formula. | Yes
Critical-failure count and IDs | Computed by formula from the scores. | Yes
Recorded route and basis | The route recorded for the run and the basis stated for it. | Yes
Consistency checks | Formula results confirming the route is compatible with the critical-failure rule. | Yes
Source file and locator | Where each transcribed value came from. | Yes
6. Recorded assumptions, gaps and limitations
• The scorecard checks internal consistency. It does not validate the underlying evidence, which is the four tests' function.
• The route is recorded, not computed. Deriving it from scores alone would misroute at least one of the four demonstrated conditions.
• A critical assurance exception count and a critical test failure count are different measures and are not added together.
• All formulas are Excel-2007-era functions so the workbook recalculates predictably.
• Gap carried: a consistency check can only detect a route that contradicts the rule. It cannot detect a route that is merely the wrong one of two permissible routes.
7. Relationship to the previous and next template
Position | Template | Relationship
Previous | CE018-SP-11 Four-Test Assurance Checklist | The checklist produces the four scores; the scorecard totals and tests them.
This template | CE018-SP-12 Test and Acceptance Scorecard | Totals the scores, detects critical failures by formula and checks the recorded route for consistency.
Next | CE018-SP-13 Configured NEC4 Decision-Readiness Control Matrix | The scorecard summarises the four tests; SP-13 records the twelve configured controls behind them.
8. Retained human authority
Permitted assistant support / prohibited assistant actions
Permitted: extract; link; compare; reconcile; cite; flag; score against the configured controls; identify exceptions and owners; prepare a decision-readiness pack; recommend a controlled review route.
Prohibited: decide whether CE-018 is a compensation event; decide entitlement; determine whether the Contractor's assessment is contractually correct; accept, reject or assess a quotation; issue or draft a contractual communication; determine the contractual effect of a clause; instruct or implement CE-018; claim legal or NEC4 compliance; provide legal advice.
Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018. When reused, name the relevant contractual role or accountable decision owner.

## Blank Scorecard
CE018-SP-12
Test and Acceptance Scorecard — blank
Formula-driven. Enter values in the yellow cells only.
TEMPLATE — CONFIGURE BEFORE USE
Edit the yellow cells only. Every entry shown as [CONFIGURE] must be set by the accountable owner before this template is used on a live task.
The four score cells are pre-set to 2 to show the expected format and to let you see the formulas working. Overwrite them with the actual scores.
This blank sheet carries no CE-018 values. Do not copy worked-example values into it.
Yellow cells are inputs. Every other value on this sheet is a formula.
Enter 2, 1 or 0 for each test score. Enter the recorded route and its basis. Nothing else is typed.
The route is recorded here, not calculated. The route-priority hierarchy depends on why a test scored 0, and a score alone does not carry that reason.
Run reference | [CONFIGURE]
Evidence cut-off | [CONFIGURE]
Test | Score (input 2 / 1 / 0) | Status (formula) | Critical failure (formula) | Notes
T1 — Evidence and version | 2 | PASS | No
T2 — Records agree | 2 | PASS | No
T3 — Configured NEC4 route and clock | 2 | PASS | No
T4 — Human authority | 2 | PASS | No
Total score | 8
Maximum score | 8
Critical failure count | 0
Critical test identifiers | NONE
Critical failure present? | NO - no critical failure recorded
Score entries valid? | OK - all scores are 2, 1 or 0
Recorded decision-readiness route | [CONFIGURE]
Recorded route basis | [CONFIGURE] state why this route applies, referencing the failing test or the bounded condition.
Consistency check 1 — route against critical failure | OK
Consistency check 2 — authority failure takes first priority | OK
Consistency check 3 — no critical failure but a restrictive route recorded | OK
Issue gate | Not available as an unqualified ready recommendation - refer to the recorded route and basis
Why the route is not calculated from the scores
In one of the four demonstrated CE-018 conditions, T2 scored 0 because agreement could not be tested with a mandatory record absent — not because the records present conflicted. The issued route was REWORK EVIDENCE PACK, not STOP / RECONCILE.
A formula mapping T2 = 0 to STOP / RECONCILE would therefore return the wrong route. The score records that a control failed; it does not record why.
The scorecard records the route and its basis, then checks the two things a formula can safely check: that a ready route is not claimed over a critical failure, and that a reserved-authority failure is routed to the accountable contractual role.
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.

## Worked Example CE-018
CE018-SP-12
Test and Acceptance Scorecard — CE-018, four conditions reconciled by formula
Transcribed scores in blue. Computed values in black. The reconciliation block compares the computed values against the totals and routes transcribed separately from each issued record.
COMPLETED CE-018 WORKED EXAMPLE — ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Fictional Demonstration Data. Every value is transcribed from the final issued CE-018 scenario record and is not rerun, rescored or reinterpreted here.
Source record: the four final issued CE-018 scenario records, each read only for its own column
Read-only reference. Do not edit this sheet; copy the blank template instead.
| S1 Rev 3.0 | S2 Rev 3.1 | S3 Rev 3.4 | S4 Rev 3.2
T1 — Evidence and version | 2 | 0 | 1 | 2
T2 — Records agree | 2 | 0 | 0 | 2
T3 — Configured NEC4 route and clock | 1 | 0 | 1 | 1
T4 — Human authority | 2 | 2 | 2 | 0
Total score (computed) | 7 | 2 | 4 | 5
Maximum score (computed) | 8 | 8 | 8 | 8
Critical failure count (computed) | 0 | 3 | 1 | 1
Critical test identifiers (computed) | NONE | T1, T2, T3 | T2 | T4
Issued total, transcribed separately | 7 | 2 | 4 | 5
Issued critical failure count, transcribed separately | 0 | 3 | 1 | 1
Issued critical test identifiers, transcribed separately | NONE | T1, T2, T3 | T2 | T4
Issued decision-readiness route, transcribed separately | READY WITH CONDITIONS | REWORK EVIDENCE PACK | STOP / RECONCILE | REFER TO PROJECT MANAGER
Reconciliation — computed against issued
Total reconciles? | PASS | PASS | PASS | PASS
Critical count reconciles? | PASS | PASS | PASS | PASS
Critical identifiers reconcile? | PASS | PASS | PASS | PASS
Route consistent with the critical-failure rule? | PASS | PASS | PASS | PASS
Authority failure routed to the Project Manager? | PASS | PASS | PASS | PASS
Gate — all reconciliation checks | PASS - the four transcribed results reconcile with the issued records
What this reconciliation does and does not prove
It proves that the transcribed scores add to the issued totals, that the critical-failure counts and identifiers agree, and that no route contradicts the critical-failure rule.
It does not rerun, rescore or reinterpret any assessment, and it does not validate the underlying evidence. The four issued results are unchanged.
S4 records the highest total of the three failing conditions at 5 of 8 and still returns the most restrictive route, because the failure is at T4. The reconciliation confirms that routing, it does not produce it.
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.