## Cover
CE018-SP-13
Configured NEC4 Decision-Readiness Control Matrix
Stage 03 — Test the output ¦ Twelve configured process-assurance controls — not a legal-compliance conclusion
Document reference | CE018-SP-13
Template title | Configured NEC4 Decision-Readiness Control Matrix
Starter pack stage | 03 — Test the output
Accountable owner | NEC4 Project Manager or equivalent accountable decision owner (owns the configuration) / Project Controls Lead (runs the controls)
Version | v1.0
Status — blank template | TEMPLATE — CONFIGURE BEFORE USE
Status — worked example | ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Issue date | 2026-03-31
Project | Westbridge Station Access and Enabling Works (WSAE)
Worked example | CE-018 — Restricted access to the Platform 4 worksite
Evidence cut-off | 2026-03-31
Prepared by | CE-018 Project Controls Assurance Assistant (configured AI support, non-contractual)
Prepared for | Elena Brooks — NEC4 Project Manager
Control owner | Sofia Khan — Project Controls Lead
Classification | Fictional Demonstration Data
Previous template | CE018-SP-12 Test and Acceptance Scorecard
Next template | CE018-SP-14 Evidence Exception Report
Retained human authority
This workbook is configured Project Controls assurance support. It is not a contractual communication and it does not state NEC4 or legal compliance.
In the CE-018 worked example, Elena Brooks, NEC4 Project Manager, retains every contractual decision. In your own use, name the relevant contractual role or accountable decision owner in place of Elena Brooks.
Worksheets in this workbook
Cover — document control and retained authority
Guidance — purpose, owner, completion instructions, mandatory fields
Control Definitions — the twelve configured controls
Blank Matrix — reusable template
Worked Example CE-018 — the S3 control results
Clause 64.1 Trigger Panel — kept separate from control results

## Guidance
CE018-SP-13
How to use this template
Configured NEC4 Decision-Readiness Control Matrix
1. Purpose
The matrix runs twelve configured process-assurance controls against the registered evidence and records a result, a finding, a consequence, an owner and a criticality for each. Four of the twelve are the configured Clause 64.1 intervention trigger checks, and those are reported on a separate panel.
The controls test process readiness. They do not certify contractual compliance and they do not determine the contractual effect of any clause.
2. When to use this template
• At every assessment run, after the four tests are scored.
• At every retest of a control named in a corrective action.
• When the contract configuration changes — a period, a route or a reserved authority.
• When a trigger matter must be placed before the accountable contractual role.
3. Accountable owner
Role | Named person in the CE-018 worked example | Responsibility for this template
Configuration owner | Elena Brooks — NEC4 Project Manager | Owns the control configuration, the clause references and the permitted result values.
Control operator | Sofia Khan — Project Controls Lead | Runs the twelve controls and records findings with citations.
Named control owners | Marcus Reed; Elena Brooks; Planning Manager | Own the controls attributed to them and the actions arising.
Configured AI support | CE-018 Assurance Assistant | Reports objective evidence findings against each control. Does not determine contractual effect or trigger status.
4. Completion instructions
1. Run all twelve controls at every assessment. A control not run is recorded as not run, never as passed.
2. Record the result using the permitted result values configured for that control. Do not invent a new result value.
3. Keep the control result and the Clause 64.1 trigger status in separate fields. A control can fail as a process control while its trigger status remains reserved to the accountable contractual role.
4. Report the trigger checks on the separate panel. Only four of the twelve controls carry a trigger; the remaining eight are recorded as not applicable.
5. Cite the evidence for every result: file name, record identifier and approved revision.
6. Record the criticality as configured, not as felt. Criticality is a property of the control, not of the run.
7. Where a result is reserved to the accountable contractual role, record it as such and route it as a referral, not as an action to be closed by retest.
8. Never describe a set of control results as NEC4 or legal compliance.
5. Minimum mandatory fields
Field | What it must record | Mandatory
Control ID and group | NEC-01 to NEC-12 and the control group. | Yes
Clause reference | The configured clause reference for the control. | Yes
Four-test link | Which of T1 to T4 the control supports. | Yes
Decision-readiness question | The question the control answers. | Yes
Result | One of the permitted result values configured for that control. | Yes
Evidence finding | What the registered evidence shows. | Yes
Consequence | What the result prevents or permits. | Yes
Accountable owner | The named owner of the control outcome. | Yes
Criticality | The configured criticality of the control. | Yes
Clause 64.1 trigger reference and status | The trigger, where the control carries one; otherwise recorded as not applicable. | Yes
Evidence citation | File name, record identifier and approved revision. | Yes
6. Recorded assumptions, gaps and limitations
• These are configured process-assurance controls for a fictional demonstration. They are not a certification of contractual compliance and are not legal advice.
• A control result and a Clause 64.1 trigger status are separate fields and must never be merged into one measure.
• Only four of the twelve controls carry a trigger. The other eight are recorded as not a trigger control and not applicable, so any trigger count must filter on the trigger reference.
• The demonstration applies base NEC4 ECC process with no relevant Z-clause amendment configured for the selected clauses. Configured periods are one week, three weeks and two weeks as recorded against the relevant controls.
• Where a source record does not state a consequence at control level, the absence is marked rather than filled from another condition.
• Gap carried: the controls test presence, linkage and timing. They do not test whether a programme or an assessment is contractually acceptable — that judgement is reserved.
7. Relationship to the previous and next template
Position | Template | Relationship
Previous | CE018-SP-12 Test and Acceptance Scorecard | The scorecard summarises the four tests; this matrix records the twelve controls behind them.
This template | CE018-SP-13 Configured NEC4 Decision-Readiness Control Matrix | Runs and records the twelve configured controls, with the four trigger checks reported separately.
Next | CE018-SP-14 Evidence Exception Report | Control results other than a pass become exceptions in SP-14.
8. Retained human authority
Permitted assistant support / prohibited assistant actions
Permitted: extract; link; compare; reconcile; cite; flag; score against the configured controls; identify exceptions and owners; prepare a decision-readiness pack; recommend a controlled review route.
Prohibited: decide whether CE-018 is a compensation event; decide entitlement; determine whether the Contractor's assessment is contractually correct; accept, reject or assess a quotation; issue or draft a contractual communication; determine the contractual effect of a clause; instruct or implement CE-018; claim legal or NEC4 compliance; provide legal advice.
Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018. When reused, name the relevant contractual role or accountable decision owner.

## Control Definitions
CE018-SP-13
The twelve configured controls
Transcribed from NEC4_Decision_Readiness_Control_Matrix.csv (CTRL-007) Rev 1.0. Configured process-assurance checks for a fictional demonstration — not a legal-compliance standard.
Presentation boundary
NEC4 references here are configured decision-readiness and process-assurance checks. They are not a certification of contractual compliance and they are not legal advice.
The matrix distinguishes objective evidence findings, configured control results, Project Manager judgement and retained contractual authority. Those four are never collapsed into one statement.
Control | Control group | Test link | Clause reference | Decision-readiness question | Required evidence | Common failure mode | Permitted result values | Criticality | Human judgement boundary
NEC-01 | Early warning | T1/T3 | 15.1 | Is there dated evidence that the access risk was warned when it became apparent? | Initial risk email; EW-006; Early Warning Register reference | No warning, late warning or no record of the warning | PASSED; CONDITIONAL; FAILED_REWORK; PM_JUDGEMENT | Major | Assistant compares dated evidence but does not decide the contractual effect of timing
NEC-02 | Access and event basis | T1/T3 | 33.1 / 60.1(2) | Do the Accepted Programme and access record evidence the planned access date and the actual restriction? | AP12; access confirmation; CE notification | No controlled access date, no restriction evidence or inconsistent event description | EVIDENCED_PM_DETERMINATION; FAILED_REWORK; STOP_ESCALATE | Critical evidence and authority | Assistant must not decide whether the event is a compensation event or determine entitlement
NEC-03 | Contractor notification | T1/T3 | 61.3 | Was the Contractor notification separately recorded, correctly routed and within the configured time-bar control? | CE-018 notification; event date; source register | Notification absent, not separate from EW, wrong role or potential time-bar breach | PASSED; CONDITIONAL; FAILED_REWORK; STOP_PM_JUDGEMENT | Critical | Assistant calculates elapsed time but does not decide whether an exception to the time bar applies
NEC-04 | PM notification response | T3 | 61.4 | Did the Project Manager respond within the configured one-week period? | CE notification; PM response; RC-01 | Missing or overdue Project Manager response | PASSED; PENDING_NOT_DUE; STOP_ESCALATE | Critical clock | Assistant reports the clock and evidence; Project Manager determines contractual effect
NEC-05 | Quotation content | T1/T2/T3 | 62.2 | Does the quotation pack contain assessment details and, where remaining work is altered, the required alterations to the Accepted Programme? | Quotation Rev B; submission email; AP12; programme alteration/current update; calculation basis | Cost-only quotation, unsupported assessment, missing programme alteration or unclear dividing-date basis | PASSED; CONDITIONAL; FAILED_REWORK; PM_JUDGEMENT | Critical content | Assistant checks presence and consistency; Project Manager judges whether the assessment is contractually correct
NEC-06 | Quotation submission clock | T3 | 62.3 | Was the quotation and assessment detail submitted within the configured three-week period? | PM request; quotation submission; RC-02 | Late or missing quotation/assessment details | PASSED; CONDITIONAL; FAILED_PM_ASSESSMENT_TRIGGER | Critical clock | Assistant calculates the clock but does not decide whether an agreed extension applies unless evidenced
NEC-07 | PM quotation response | T3/T4 | 62.3 / 62.6 | Is the Project Manager response recorded, or correctly classified as pending-not-due at the cut-off? | Quotation submission; RC-03; decision record | Overdue response, missing decision record or assistant attempts the response | PASSED; PENDING_NOT_DUE; STOP_ESCALATE | Critical clock and authority | Assistant must not respond, accept, assess or issue the contractual communication
NEC-08 | Clause 64.1 trigger 1 | T2/T3 | 64.1 - late/missing quotation | Has the Contractor failed to submit the quotation and assessment details within the permitted time? | PM request; quotation; submission email; RC-02 | Quotation or assessment details missing or late | NOT_TRIGGERED; TRIGGERED_PM_ASSESSMENT; PM_JUDGEMENT | Critical | Assistant identifies the objective trigger evidence; Project Manager determines and performs the assessment
NEC-09 | Clause 64.1 trigger 2 | T2/T3 | 64.1 - incorrect assessment | Is there a material inconsistency or unsupported basis that may indicate the Contractor's assessment is not correct? | Quotation; programme; forecast; risk; change; calculations | Unsupported or irreconcilable time/cost assessment | NO_EVIDENCE_DEFECT; TRIGGER_INDICATED; PM_JUDGEMENT | Critical judgement | Only the Project Manager decides whether the assessment is contractually correct
NEC-10 | Clause 64.1 trigger 3 | T1/T2/T3 | 62.2 / 64.1 - programme alteration missing | Where the event alters remaining work, was the required programme or alteration submitted with the quotation pack? | Submission email; AP12; UP13 or specific programme alteration; quotation narrative | Required programme/alteration absent or not linked to the quotation | NOT_TRIGGERED; TRIGGERED_PM_ASSESSMENT; FAILED_REWORK | Critical | Assistant checks presence and linkage, not programme acceptability
NEC-11 | Clause 64.1 trigger 4 | T1/T3 | 31.1 / 31.3 / 32.2 / 64.1 - latest programme not accepted | Is an Accepted Programme available and is any relevant non-acceptance status identified? | AP12 acceptance status; programme submissions; PM acceptance/non-acceptance record | No Accepted Programme or latest programme not accepted for a contract reason | NOT_TRIGGERED; TRIGGERED_PM_ASSESSMENT; PM_JUDGEMENT | Critical | Assistant distinguishes AP12 from UP13 and must not treat an update as accepted without evidence
NEC-12 | Retained human authority | T4 | Clauses 61-64 and Authority Matrix | Are the remaining notification, assessment, acceptance, instruction and implementation actions reserved to the named NEC4 role? | Actor Authority Matrix; control brief; route rules; requested action | Assistant or unauthorised person attempts a contractual decision or communication | PASSED; FAILED_STOP_REFER | Critical authority | Assistant may prepare and recommend a route but must not take the contractual action
Trigger controls are a subset
Only NEC-08 to NEC-11 carry a configured Clause 64.1 intervention trigger, mapping to triggers 1 to 4. The other eight controls carry no trigger.
Any count of triggers must therefore filter on the trigger reference. Counting all twelve controls as trigger controls overstates the trigger position fourfold.
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.

## Blank Matrix
CE018-SP-13
Configured NEC4 Decision-Readiness Control Matrix — blank
Reusable template. One row per control. Keep the result and the trigger status in separate columns.
TEMPLATE — CONFIGURE BEFORE USE
Edit the white cells only. Every entry shown as [CONFIGURE] must be set by the accountable owner before this template is used on a live task.
Row marked EXAMPLE FORMAT shows the expected format of an entry. Delete that row before use — it is not data.
This blank sheet carries no CE-018 values. Do not copy worked-example values into it.
Two columns that must never be merged
Result records the configured process-control outcome. Clause 64.1 trigger status records the trigger position, where the control carries one.
A control can fail as a process control while its trigger status remains reserved to the accountable contractual role. Merging the two would misstate both.
Control | Control group | Test link | Clause reference | Decision-readiness question | Result | Evidence finding | Consequence | Accountable owner | Criticality | Clause 64.1 trigger reference | Clause 64.1 trigger status | Evidence citation
NEC-01 | [CONFIGURE] | T1/T3 | [CONFIGURE] | [CONFIGURE] the question this control answers | [CONFIGURE from the permitted values] | EXAMPLE FORMAT — [CONFIGURE] what the registered evidence shows | [CONFIGURE] what the result prevents or permits | [CONFIGURE] | [CONFIGURE] | Not a Clause 64.1 trigger control | Not applicable | [CONFIGURE] file / record ID / revision
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.

## Worked Example CE-018
CE018-SP-13
Configured NEC4 Control Matrix — CE-018 scenario S3 Rev 3.4
Twelve controls run. Configured process-assurance result: CONFIGURED NEC4 PROCESS CONTROL FAILURE — STOP / RECONCILE.
COMPLETED CE-018 WORKED EXAMPLE — ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Fictional Demonstration Data. Every value is transcribed from the final issued CE-018 scenario record and is not rerun, rescored or reinterpreted here.
Source record: CE018_S3_NEC4_Decision_Readiness_Result_Rev3_4.json — nec4_control_results
Read-only reference. Do not edit this sheet; copy the blank template instead.
Result and trigger status are held apart
NEC-09, NEC-10 and NEC-11 return PM_JUDGEMENT as a control result and PROJECT MANAGER JUDGEMENT as a trigger status. They are recorded in two separate columns and are not merged.
No control in any of the four demonstrated conditions records a trigger status of TRIGGER_INDICATED.
This is a configured process-assurance result. It is not a statement of NEC4 or legal compliance and it is not legal advice.
Control | Control group | Test link | Clause reference | Decision-readiness question | Result | Evidence finding | Consequence | Accountable owner | Criticality | Clause 64.1 trigger reference | Clause 64.1 trigger status | Evidence citation
NEC-01 | Early warning | T1/T3 | 15.1 | Is there dated evidence that the access risk was warned when it became apparent? | PASSED | The operational constraint was raised 2026-02-24 and the Contractor's early warning was recorded 2026-02-25, meeting the configured RC-EW due date of 2026-02-25. EW-006 and CE-018 remain separate records; the early warning did not become the compensation event. | Objective dates met. Whether the warning was sufficiently prompt in contractual terms remains a Project Manager judgement. | Marcus Reed / Elena Brooks | Major | Not a Clause 64.1 trigger control | Not applicable | Email_01_Access_Risk_2026-02-24.eml / CORR-001 Rev 1.0; Email_02_EW006_2026-02-25.eml / EW-006 Rev 1.0; Route_Clock_Rules.csv / CTRL-003 row RC-EW
NEC-02 | Access and event basis | T1/T3 | 33.1 / 60.1(2) | Do the Accepted Programme and access record evidence the planned access date and the actual restriction? | EVIDENCED_PM_DETERMINATION | AP12 evidences the planned access date of 2026-03-04. ACC-004 evidences that the planned 8-hour window was not available and that a 2-hour escorted window was provided instead. The candidate event basis is evidenced and referred to the Project Manager. | The assistant evidences the candidate basis only. It has not decided and must not decide that a compensation event exists or that entitlement follows. | Elena Brooks | Critical evidence and authority | Not a Clause 64.1 trigger control | Not applicable | P6_Activity_Export_AP12.csv / PROG-AP12, WSAE-A1200 (planned 2026-03-04); Email_03_Access_Restriction_2026-03-04.eml / ACC-004 Rev 1.0; Email_04_CE018_Notification_2026-03-05.eml / CE-018 Rev 1.0
NEC-03 | Contractor notification | T1/T3 | 61.3 | Was the Contractor notification separately recorded, correctly routed and within the configured time-bar control? | PASSED | The notification was issued by Marcus Reed to Elena Brooks on 2026-03-05, one working day after the 2026-03-04 restriction, and is recorded separately from EW-006 under its own record ID and Message-ID. Routing matches the Authority Matrix. No separate Clause 61.3 period is configured in Route_Clock_Rules.csv, so only the objective elapsed time is reported. | No time-bar concern arises on the objective dates. Whether any contractual exception applies is not decided by the assistant. | Marcus Reed | Critical | Not a Clause 64.1 trigger control | Not applicable | Email_04_CE018_Notification_2026-03-05.eml / CE-018 Rev 1.0; Email_02_EW006_2026-02-25.eml / EW-006 Rev 1.0; Source_Register.csv / SRC-001 Rev 3.0
NEC-04 | PM notification response | T3 | 61.4 | Did the Project Manager respond within the configured one-week period? | PASSED | RC-01 sets a trigger date of 2026-03-05 with a configured one-week period and a due date of 2026-03-12. The Project Manager response is dated 2026-03-12, on the configured date. | Configured clock met. No escalation required. | Elena Brooks | Critical clock | Not a Clause 64.1 trigger control | Not applicable | Email_05_PM_Response_2026-03-12.eml / PMR-018 Rev 1.0; Route_Clock_Rules.csv / CTRL-003 row RC-01
NEC-05 | Quotation content | T1/T2/T3 | 62.2 | Does the quotation pack contain assessment details and, where remaining work is altered, the required alterations to the Accepted Programme? | CONDITIONAL | Assessment details are present and structured: each of the five quotation lines carries WBS, activity, CBS code, cost element, amount, schedule effect and a narrative basis, and QSUB-018 expressly links AP12, UP13 and the affected activities and CBS accounts. Two conditions remain. First, no calculation build-up (rates, quantities or durations) supports the narrative basis. Second, the supporting records the Contractor cites do not agree with the quoted position, and UP13 is a current update rather than an accepted programme. | Content presence is evidenced; contractual sufficiency is not. The Clause 62.2 assessment-detail check has been explicitly performed and is reported as conditional, not satisfied. | Marcus Reed / Elena Brooks | Critical content | Not a Clause 64.1 trigger control | Not applicable | CE018_Quotation_RevB.csv / QUOT-CE018-REVB Rev B, 5 rows; Email_06_Quotation_Submission_2026-03-28.eml / QSUB-018 Rev 1.0; P6_Activity_Export_AP12.csv / PROG-AP12; P6_Activity_Export_UP13.csv / PROG-UP13
NEC-06 | Quotation submission clock | T3 | 62.3 | Was the quotation and assessment detail submitted within the configured three-week period? | PASSED | RC-02 sets a trigger date of 2026-03-12, a configured three-week period and a due date of 2026-04-02. The quotation was submitted 2026-03-28, five calendar days inside the configured period. | Configured clock met. Content adequacy is assessed separately under NEC-05 and NEC-10. | Marcus Reed | Critical clock | Not a Clause 64.1 trigger control | Not applicable | Email_06_Quotation_Submission_2026-03-28.eml / QSUB-018 Rev 1.0; CE018_Quotation_RevB.csv / QUOT-CE018-REVB Rev B; Route_Clock_Rules.csv / CTRL-003 row RC-02
NEC-07 | PM quotation response | T3/T4 | 62.3 / 62.6 | Is the Project Manager response recorded, or correctly classified as pending-not-due at the cut-off? | PENDING_NOT_DUE | RC-03 sets a trigger date of 2026-03-28, a configured two-week period and a due date of 2026-04-11. At the 2026-03-31 evidence cut-off the response is not yet due and no decision record exists. CHG-018 records decision status 'Not yet decided' with a next action due 2026-04-02. | Not overdue and does not prevent review. The assistant has not inferred, drafted or issued the Project Manager's response. | Elena Brooks | Critical clock and authority | Not a Clause 64.1 trigger control | Not applicable | Route_Clock_Rules.csv / CTRL-003 row RC-03; Change_Register.csv / CHG-018 Rev 5; CE018_Event_Record.csv / CASE-001 Rev 1.1
NEC-08 | Clause 64.1 trigger 1 | T2/T3 | 64.1 — late/missing quotation | Has the Contractor failed to submit the quotation and assessment details within the permitted time? | NOT_TRIGGERED | A quotation with assessment details was submitted on 2026-03-28, inside the configured period ending 2026-04-02. Neither the quotation nor the assessment details are absent or late. | No trigger on this limb. Content quality is reported under NEC-05, not here. | Elena Brooks | Critical | Trigger 1 | NOT_TRIGGERED | Email_05_PM_Response_2026-03-12.eml / PMR-018 Rev 1.0; Email_06_Quotation_Submission_2026-03-28.eml / QSUB-018 Rev 1.0; CE018_Quotation_RevB.csv / QUOT-CE018-REVB Rev B; Route_Clock_Rules.csv / CTRL-003 row RC-02
NEC-09 | Clause 64.1 trigger 2 | T2/T3 | 64.1 — incorrect assessment | Is there a material inconsistency or unsupported basis that may indicate the Contractor's assessment is not correct? | PM_JUDGEMENT | MATERIAL CONFLICT IDENTIFIED — PROJECT MANAGER DETERMINATION REQUIRED. Three registered records state three different time and cost positions for the same event: GBP 185,000 / 10 days, GBP 150,000 / 8 days and GBP 210,000 / 12 days. No calculation build-up supports the quoted figures, and UP13 carries an internal inconsistency between its recorded 10-day variance field and the 12 working days derived from its own dates. The registered records therefore provide objective evidence of conflicting cost and time positions. | The assistant must not decide that the Contractor assessed the compensation event incorrectly. Objective conflict is evidenced; whether that conflict means the assessment is incorrect for Clause 64.1 purposes is a determination reserved to Elena Brooks, NEC4 Project Manager. | Elena Brooks | Critical judgement | Trigger 2 | PROJECT MANAGER JUDGEMENT | CE018_Quotation_RevB.csv / QUOT-CE018-REVB Rev B; Cost_Forecast_P07_CONFLICT.csv / FCST-P07-X Rev P07-X; Risk_Register_CONFLICT.csv / RISK-044-X Rev 7-X; P6_Activity_Export_UP13.csv / PROG-UP13
NEC-10 | Clause 64.1 trigger 3 | T1/T2/T3 | 62.2 / 64.1 — programme alteration missing | Where the event alters remaining work, was the required programme or alteration submitted with the quotation pack? | PM_JUDGEMENT | UP13 is a periodic current programme update linked to the quotation. It evidences changed activities for WSAE-A1300, WSAE-A1400 and WSAE-M9000, and QSUB-018 expressly references AP12, UP13 and those activities. It does not conclusively establish that the specific alterations to the Accepted Programme required by Clause 62.2 were submitted as part of the quotation assessment. | The assistant must not determine contractual sufficiency. Presence and linkage of a current programme update are evidenced; whether that update constitutes the required Clause 62.2 alterations is reserved to Elena Brooks. This treatment is consistent with the approved S1 treatment of the same programme evidence. | Marcus Reed / Elena Brooks | Critical | Trigger 3 | PROJECT MANAGER JUDGEMENT | Email_06_Quotation_Submission_2026-03-28.eml / QSUB-018 Rev 1.0; P6_Activity_Export_UP13.csv / PROG-UP13; P6_Activity_Export_AP12.csv / PROG-AP12; CE018_Quotation_RevB.csv / QUOT-CE018-REVB Rev B
NEC-11 | Clause 64.1 trigger 4 | T1/T3 | 31.1 / 31.3 / 32.2 / 64.1 — latest programme not accepted | Is an Accepted Programme available and is any relevant non-acceptance status identified? | PM_JUDGEMENT | An Accepted Programme is available: AP12 is registered and carries accepted status, and it has not been substituted by UP13 anywhere in this assessment. However, no Project Manager acceptance or non-acceptance record exists for UP13 in the registered evidence, so its status can be neither confirmed nor excluded without inference. | Referred to the Project Manager. The assistant distinguishes AP12 from UP13 and does not treat an update as accepted without evidence. | Elena Brooks | Critical | Trigger 4 | PROJECT MANAGER JUDGEMENT | P6_Activity_Export_AP12.csv / PROG-AP12 Rev AP12 (programme_status 'Accepted Programme'); P6_Activity_Export_UP13.csv / PROG-UP13 Rev UP13 (programme_status 'Current Update'); Source_Register.csv / SRC-001 Rev 3.0
NEC-12 | Retained human authority | T4 | Clauses 61-64 and Authority Matrix | Are the remaining notification, assessment, acceptance, instruction and implementation actions reserved to the named NEC4 role? | PASSED | All remaining contractual actions — the Clause 62.3/62.6 response, any Clause 64.1 determination, acceptance or rejection of the quotation, and implementation — are reserved to Elena Brooks and are recorded as reserved in this pack. The assistant prepared cited review material only and took no reserved action. | No authority breach. The route is not driven by an authority failure. | Elena Brooks | Critical authority | Not a Clause 64.1 trigger control | Not applicable | Actor_Authority_Matrix.csv / CTRL-002 Rev 2.1, rows EB, MR, SK, AI; CE018_Control_Brief.txt / CTRL-001 Rev 3.0, Prohibited Actions and Retained Authority
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.

## Clause 64.1 Trigger Panel
CE018-SP-13
Clause 64.1 trigger panel — reported separately from control results
Four configured intervention trigger checks. Only NEC-08 to NEC-11 carry a trigger; the other eight controls are recorded as not applicable.
Reporting rule
Trigger status is reported separately from the control result in every output. The two are different statements and are never combined into a single measure.
Any trigger count must filter on the trigger reference. Eight of the twelve controls carry no trigger at all.
The assistant reports the objective evidence finding. Whether a trigger is contractually activated is determined by the accountable contractual role.
Trigger | Control | Trigger subject | S1 Rev 3.0 | S2 Rev 3.1 | S3 Rev 3.4 | S4 Rev 3.2 | Determination reserved to
Trigger 1 | NEC-08 | Quotation and assessment details not submitted within the permitted time | NOT_TRIGGERED | NOT_TRIGGERED | NOT_TRIGGERED | NOT_TRIGGERED | Elena Brooks — NEC4 Project Manager
Trigger 2 | NEC-09 | Material inconsistency or unsupported basis that may indicate the assessment is not correct | PROJECT MANAGER JUDGEMENT | PROJECT MANAGER JUDGEMENT | PROJECT MANAGER JUDGEMENT | PROJECT MANAGER JUDGEMENT | Elena Brooks — NEC4 Project Manager
Trigger 3 | NEC-10 | Required programme or alteration not submitted with the quotation pack | PROJECT MANAGER JUDGEMENT | PROJECT MANAGER JUDGEMENT | PROJECT MANAGER JUDGEMENT | PROJECT MANAGER JUDGEMENT | Elena Brooks — NEC4 Project Manager
Trigger 4 | NEC-11 | Accepted Programme availability and any relevant non-acceptance status | NOT_TRIGGERED | PROJECT MANAGER JUDGEMENT | PROJECT MANAGER JUDGEMENT | NOT_TRIGGERED | Elena Brooks — NEC4 Project Manager
Trigger position across the four conditions
No condition records a trigger status of TRIGGER_INDICATED. Trigger 1 is NOT_TRIGGERED in all four.
Triggers 2 and 3 remain reserved to Project Manager judgement in all four conditions. Trigger 4 is NOT_TRIGGERED in S1 and S4 and reserved to judgement in S2 and S3.
In S2, control NEC-10 returns FAILED_REWORK as a process control while trigger 3 remains PROJECT MANAGER JUDGEMENT. That is the clearest illustration of why the two fields are held apart.
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.