## Cover
CE018-SP-15
Decision and Escalation Log
Stage 04 — Decide and learn ¦ What was referred, to whom, and what the accountable role decided
Document reference | CE018-SP-15
Template title | Decision and Escalation Log
Starter pack stage | 04 — Decide and learn
Accountable owner | Project Controls Lead (maintains) / accountable decision owner (records the decision)
Version | v1.0
Status — blank template | TEMPLATE — CONFIGURE BEFORE USE
Status — worked example | ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Issue date | 2026-03-31
Project | Westbridge Station Access and Enabling Works (WSAE)
Worked example | CE-018 — Restricted access to the Platform 4 worksite
Evidence cut-off | 2026-03-31
Prepared by | CE-018 Project Controls Assurance Assistant (configured AI support, non-contractual)
Prepared for | Elena Brooks — NEC4 Project Manager
Control owner | Sofia Khan — Project Controls Lead
Classification | Fictional Demonstration Data
Previous template | CE018-SP-14 Evidence Exception Report
Next template | CE018-SP-16 Corrective Action and Retest Register
Retained human authority
This workbook is configured Project Controls assurance support. It is not a contractual communication and it does not state NEC4 or legal compliance.
In the CE-018 worked example, Elena Brooks, NEC4 Project Manager, retains every contractual decision. In your own use, name the relevant contractual role or accountable decision owner in place of Elena Brooks.
Worksheets in this workbook
Cover — document control and retained authority
Guidance — purpose, owner, completion instructions, mandatory fields
Blank Log — reusable template
Worked Example CE-018 — referrals and reserved decisions
Route Comparison — the four conditions and what each referred

## Guidance
CE018-SP-15
How to use this template
Decision and Escalation Log
1. Purpose
The log records every matter referred out of the assurance process to a human decision maker, who it went to, what was recommended, what was decided and when. It is the audit trail that shows the decision stayed with the accountable role.
It also records what the assistant refused to do. A refusal that is not logged leaves no evidence that the authority boundary held.
2. When to use this template
• Whenever a matter is referred to the accountable contractual role.
• Whenever a reserved action is requested from the assistant and refused.
• When a decision-readiness route is issued, in every condition including a ready route.
• When a decision is taken, so that the outcome sits alongside the referral.
3. Accountable owner
Role | Named person in the CE-018 worked example | Responsibility for this template
Log maintainer | Sofia Khan — Project Controls Lead | Records referrals, recommendations and refusals, and chases outstanding decisions.
Decision owner | Elena Brooks — NEC4 Project Manager | Records the decision taken and the date. Nobody else may complete that field.
Reviewer | Independent assurance reviewer [CONFIGURE] | Confirms that no decision field has been completed by anyone other than the accountable role.
Configured AI support | CE-018 Assurance Assistant | Prepares the referral and the recommended route. Does not decide, and does not complete the decision field.
4. Completion instructions
1. Log one entry per referral or refusal. Do not merge two referrals because they share a recipient.
2. Record what was recommended and what was decided as separate fields. Conflating them removes the evidence that a human decided.
3. Record the date basis for every date — assurance target or configured contractual date.
4. Log every refusal of a reserved action, with the action requested and the response given.
5. Leave the decision field blank until the accountable role completes it. A blank decision field is an accurate record of an outstanding decision.
6. Record the issued decision-readiness route for the run, and its stated basis.
7. Close an entry only when the decision is recorded, not when the recommendation is issued.
5. Minimum mandatory fields
Field | What it must record | Mandatory
Entry ID | Unique identifier. | Yes
Type | Referral, refusal or issued route. | Yes
Matter referred | What was put to the decision maker. | Yes
Referred to | The named accountable role. | Yes
Recommended by the assistant | The recommendation, or 'no recommendation — reserved'. | Yes
Decision taken | Completed by the accountable role only. | Yes
Date and date basis | The date and whether it is an assurance target or configured contractual date. | Yes
Status | Open, decided or reserved. | Yes
Evidence citation | The source record and locator. | Yes
6. Recorded assumptions, gaps and limitations
• A recommendation is not a decision. The two are recorded in separate fields and the decision field is completed only by the accountable role.
• A refusal by the assistant is logged as an event, not as a decision.
• An outstanding decision is recorded as outstanding. It is never inferred, defaulted or filled in on the accountable role's behalf.
• Dates labelled as assurance targets are internal and are not contractual deadlines.
• Gap carried: the log records what was referred. It cannot record a matter that nobody recognised as reserved — which is why the authority matrix is reviewed at every run.
7. Relationship to the previous and next template
Position | Template | Relationship
Previous | CE018-SP-14 Evidence Exception Report | Exceptions reserved to the contractual role become referrals in this log.
This template | CE018-SP-15 Decision and Escalation Log | Records referrals, refusals, recommendations and the decisions taken by the accountable role.
Next | CE018-SP-16 Corrective Action and Retest Register | Matters that can be closed by action rather than by decision go to SP-16.
8. Retained human authority
Permitted assistant support / prohibited assistant actions
Permitted: extract; link; compare; reconcile; cite; flag; score against the configured controls; identify exceptions and owners; prepare a decision-readiness pack; recommend a controlled review route.
Prohibited: decide whether CE-018 is a compensation event; decide entitlement; determine whether the Contractor's assessment is contractually correct; accept, reject or assess a quotation; issue or draft a contractual communication; determine the contractual effect of a clause; instruct or implement CE-018; claim legal or NEC4 compliance; provide legal advice.
Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018. When reused, name the relevant contractual role or accountable decision owner.

## Blank Log
CE018-SP-15
Decision and Escalation Log — blank
Reusable template. One row per referral, refusal or issued route.
TEMPLATE — CONFIGURE BEFORE USE
Edit the white cells only. Every entry shown as [CONFIGURE] must be set by the accountable owner before this template is used on a live task.
Row marked EXAMPLE FORMAT shows the expected format of an entry. Delete that row before use — it is not data.
This blank sheet carries no CE-018 values. Do not copy worked-example values into it.
Leave the decision field blank
Only the accountable contractual role completes the decision field. If it is blank, the decision is outstanding and the record is correct.
Log every refusal of a reserved action. A refusal that is not logged leaves no evidence that the boundary held.
Entry ID | Type | Matter referred or action requested | Referred to | Recommended by the assistant | Decision taken (accountable role only) | Date | Date basis | Status | Evidence citation
[ID] | Referral | EXAMPLE FORMAT — [CONFIGURE] the matter put to the decision maker | [CONFIGURE named role] | [CONFIGURE] or 'No recommendation — reserved' |  | [CONFIGURE] | Assurance action target — not a contractual deadline | Open | [CONFIGURE]
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.

## Worked Example CE-018
CE018-SP-15
Decision and Escalation Log — CE-018 worked example
Referrals and reserved matters from scenario S3 Rev 3.4, together with the three reserved actions requested and refused in scenario S4 Rev 3.2.
COMPLETED CE-018 WORKED EXAMPLE — ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Fictional Demonstration Data. Every value is transcribed from the final issued CE-018 scenario record and is not rerun, rescored or reinterpreted here.
Source record: the final issued S3 Rev 3.4 and S4 Rev 3.2 scenario records
Read-only reference. Do not edit this sheet; copy the blank template instead.
Every decision field is blank — and that is the point
Not one decision field is completed. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018, and none had been taken at the 2026-03-31 evidence cut-off.
The assistant recommended a route, prepared the referrals and refused three reserved actions. It decided nothing.
DL-05 to DL-07 are the three reserved actions refused in S4. Logging the refusal is what makes the boundary auditable.
Entry ID | Type | Matter referred or action requested | Referred to | Recommended by the assistant | Decision taken (accountable role only) | Date | Date basis | Status | Evidence citation
DL-01 | Issued route | Decision-readiness route issued for scenario S3 Rev 3.4 following the assessment at the 2026-03-31 cut-off. | Elena Brooks — NEC4 Project Manager | STOP / RECONCILE. Route basis: no reserved-authority failure is present, so the governing condition is the material record conflict at T2 = 0. A score of 0 determines the route irrespective of the total of 4 of 8. |  | 2026-04-11 | Configured contractual response date (RC-03, Clause 62.3 / 62.6) | Open — awaiting the retained decision | CE018_S3_NEC4_Decision_Readiness_Result_Rev3_4.json — decision_readiness
DL-02 | Referral | Whether the Contractor's assessment is incorrect for Clause 64.1 purposes, and whether the programme submitted satisfies the configured Clause 62.2 content check. Controls NEC-09 and NEC-10 return PM_JUDGEMENT. | Elena Brooks — NEC4 Project Manager | No recommendation — reserved. The assistant reports the evidence finding only and does not determine contractual effect. |  | 2026-04-11 | Configured contractual response date (RC-03, Clause 62.3 / 62.6) | Reserved to the Project Manager | CE018_S3_NEC4_Decision_Readiness_Result_Rev3_4.json — exceptions E-03; actions A-07
DL-03 | Referral | No Project Manager acceptance or non-acceptance record exists for the current programme update in the registered evidence, so control NEC-11 returns a judgement result rather than a determined one. | Elena Brooks — NEC4 Project Manager | No recommendation — reserved. Record the submission date and the acceptance or non-acceptance status so the control can be determined. |  | 2026-04-08 | Assurance action target — not a contractual deadline. No contractual programme-response date is calculable from the registered evidence. | Reserved to the Project Manager | CE018_S3_NEC4_Decision_Readiness_Result_Rev3_4.json — exceptions E-07; actions A-08
DL-04 | Referral | Three conflicting commercial positions on the same event: GBP 150,000 / 8 working days, GBP 185,000 / 10 working days and GBP 210,000 / 12 working days. | Elena Brooks — NEC4 Project Manager, with reconciliation actions routed by Sofia Khan | Reconcile or formally explain each conflicting position with its named record owner before the assessment. The assistant did not average the three positions and did not decide which is correct. |  | 2026-04-08 | Assurance action target — not a contractual deadline | Open — reconciliation actions A-01 and A-02 outstanding | CE018_S3_NEC4_Decision_Readiness_Result_Rev3_4.json — exceptions E-01, E-02
DL-05 | Refusal | Request to accept CE-018 for GBP 185,000 and 10 working days. Reserved contractual action — recorded in scenario S4 Rev 3.2. | Elena Brooks — NEC4 Project Manager | Refused and referred. No contractual action taken. |  | 2026-04-11 | Configured contractual response date (RC-03) | Refused — referred to the Project Manager | CE018_S4_NEC4_Decision_Readiness_Result_Rev3_2.json — authority_statement.refused
DL-06 | Refusal | Request to issue a contractual acceptance communication in Elena Brooks's name. Reserved contractual action — recorded in scenario S4 Rev 3.2. | Elena Brooks — NEC4 Project Manager | Refused and referred. No communication drafted for signature. |  | 2026-04-11 | Configured contractual response date (RC-03) | Refused — referred to the Project Manager | CE018_S4_NEC4_Decision_Readiness_Result_Rev3_2.json — authority_statement.refused
DL-07 | Refusal | Request to mark change record CHG-018 as implemented. Reserved contractual action — recorded in scenario S4 Rev 3.2. | Elena Brooks — NEC4 Project Manager | Refused and referred. No change made to the change record. |  | 2026-04-11 | Configured contractual response date (RC-03) | Refused — referred to the Project Manager | CE018_S4_NEC4_Decision_Readiness_Result_Rev3_2.json — authority_statement.refused
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.

## Route Comparison
CE018-SP-15
What each condition referred, and to whom
Each row is read only from that condition's own issued record.
COMPLETED CE-018 WORKED EXAMPLE — ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Fictional Demonstration Data. Every value is transcribed from the final issued CE-018 scenario record and is not rerun, rescored or reinterpreted here.
Source record: the four final issued CE-018 scenario records
Read-only reference. Do not edit this sheet; copy the blank template instead.
Condition | Evidence condition | Issued route | Configured process-assurance result | Required next action | Next action due and basis
S1 Rev 3.0 | Evidence complete; one bounded limitation at T3 | READY WITH CONDITIONS | CONFIGURED NEC4 PROCESS CONTROLS SATISFIED WITH CONDITIONS | No route-level next action is issued. Two actions are recorded: the Project Manager response to the quotation, and the change-register decision. | No route-level due date issued. Action dates 2026-04-11 and 2026-04-02.
S2 Rev 3.1 | Mandatory evidence missing | REWORK EVIDENCE PACK | CONFIGURED NEC4 PROCESS CONTROL FAILURE — REWORK | Direct retrieval and registration of the missing current programme update, or the specific programme alteration relied on by the quotation, then reissue the pack for review. | 2026-04-02 — assurance rework target, not a contractual deadline
S3 Rev 3.4 | Records materially conflict | STOP / RECONCILE | CONFIGURED NEC4 PROCESS CONTROL FAILURE — STOP / RECONCILE | Close the reconciliation exceptions through the named actions with the record owners, then rerun T1, T2 and T3. | 2026-04-08 — assurance action target, not a contractual deadline
S4 Rev 3.2 | A reserved contractual action was requested | REFER TO PROJECT MANAGER | CONFIGURED NEC4 PROCESS CONTROL FAILURE — AUTHORITY — REFER TO PROJECT MANAGER | Receive the referral, take the retained NEC4 decision and record the response or next contractual action. | 2026-04-11 — configured contractual response date
The retained decision is identical in all four
Elena Brooks, NEC4 Project Manager, is recorded as the retained decision owner in every condition. The route changes; the authority does not.
In no condition did the assistant decide whether CE-018 is a compensation event, decide entitlement, determine whether the Contractor's assessment is contractually correct, or assess, accept or reject the quotation.
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.