## Cover
CE018-SP-16
Corrective Action and Retest Register
Stage 04 — Decide and learn ¦ What must be fixed, by whom, by when — and exactly what is rerun on closure
Document reference | CE018-SP-16
Template title | Corrective Action and Retest Register
Starter pack stage | 04 — Decide and learn
Accountable owner | Project Controls Lead (maintains) / named record owners (close the actions)
Version | v1.0
Status — blank template | TEMPLATE — CONFIGURE BEFORE USE
Status — worked example | ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Issue date | 2026-03-31
Project | Westbridge Station Access and Enabling Works (WSAE)
Worked example | CE-018 — Restricted access to the Platform 4 worksite
Evidence cut-off | 2026-03-31
Prepared by | CE-018 Project Controls Assurance Assistant (configured AI support, non-contractual)
Prepared for | Elena Brooks — NEC4 Project Manager
Control owner | Sofia Khan — Project Controls Lead
Classification | Fictional Demonstration Data
Previous template | CE018-SP-15 Decision and Escalation Log
Next template | CE018-SP-17 Assurance Lessons-Learned Record
Retained human authority
This workbook is configured Project Controls assurance support. It is not a contractual communication and it does not state NEC4 or legal compliance.
In the CE-018 worked example, Elena Brooks, NEC4 Project Manager, retains every contractual decision. In your own use, name the relevant contractual role or accountable decision owner in place of Elena Brooks.
Worksheets in this workbook
Cover — document control and retained authority
Guidance — purpose, owner, completion instructions, mandatory fields
Blank Register — reusable template
Worked Example CE-018 — the S3 action set
Retest Scope — what each condition must rerun

## Guidance
CE018-SP-16
How to use this template
Corrective Action and Retest Register
1. Purpose
The register records every corrective action arising from the assurance run: what must be done, by whom, by when, on what date basis, and precisely which tests and controls are rerun when it closes.
Naming the retest scope at the point the action is raised is what makes closure verifiable. An action closed without a retest has changed the evidence but not the assurance result.
2. When to use this template
• Immediately after the exception report is issued.
• When an action is closed, to record the closure evidence and trigger the retest.
• When an action date moves, so the change and its reason are visible.
• Before reissuing an assurance pack after rework.
3. Accountable owner
Role | Named person in the CE-018 worked example | Responsibility for this template
Register maintainer | Sofia Khan — Project Controls Lead | Maintains the register, confirms closure evidence and runs the retests.
Action owners | Planning Manager; Risk Manager; Marcus Reed — Contractor Delivery Lead; Commercial Manager | Close the actions raised against their records and supply the closure evidence.
Reserved matters | Elena Brooks — NEC4 Project Manager | Records determinations on matters reserved to the contractual role; these are not closed by assurance retest.
Configured AI support | CE-018 Assurance Assistant | Raises actions with owners, dates and retest scope, and reruns the named tests on closure. Does not close an action and does not accept closure evidence.
4. Completion instructions
1. Raise one action per exception. Where one exception needs two different owners to act, raise two actions.
2. Name a single accountable owner for each action. An action owned by a team is owned by nobody.
3. Record the dependency — the exception the action closes — so that closure can be traced back.
4. Give every date an explicit basis. An assurance action target is not a contractual deadline and must never be presented as one.
5. State the retest scope at the point the action is raised: the specific tests and controls to be rerun.
6. Where a matter is reserved to the accountable contractual role, mark it as reserved and record that it is not closed by assurance retest.
7. On closure, record the closure evidence, run the named retests and record the retest outcome.
8. Do not close an action on the basis that the due date has passed.
5. Minimum mandatory fields
Field | What it must record | Mandatory
Action ID | Unique identifier. | Yes
Action | What must be done, stated as an action. | Yes
Accountable owner | One named owner. | Yes
Dependency | The exception the action closes. | Yes
Due date and date basis | The date and whether it is an assurance target or a configured contractual date. | Yes
Status | Open, closed or reserved to the accountable contractual role. | Yes
Retest scope | The specific tests and controls rerun on closure. | Yes
Closure evidence | The record that evidences closure. | Yes
Retest outcome | The result of the rerun. | Yes
6. Recorded assumptions, gaps and limitations
• An action changes the evidence. Only the retest changes the assurance result.
• A matter reserved to the accountable contractual role is not closed by assurance retest; its closure is a recorded determination.
• Dates labelled as assurance targets are internal rework dates and are not contractual deadlines.
• Closing every action does not guarantee a different route. The retest determines that, and it may return the same result.
• Gap carried: the register records actions arising from what the assessment found. It cannot raise an action against a defect that no registered record reveals.
7. Relationship to the previous and next template
Position | Template | Relationship
Previous | CE018-SP-15 Decision and Escalation Log | Matters that can be fixed by action, rather than decided, come here.
This template | CE018-SP-16 Corrective Action and Retest Register | Records corrective actions with owners, dates, date basis and the exact retest scope on closure.
Next | CE018-SP-17 Assurance Lessons-Learned Record | SP-17 records what should change so the same action is not needed again.
8. Retained human authority
Permitted assistant support / prohibited assistant actions
Permitted: extract; link; compare; reconcile; cite; flag; score against the configured controls; identify exceptions and owners; prepare a decision-readiness pack; recommend a controlled review route.
Prohibited: decide whether CE-018 is a compensation event; decide entitlement; determine whether the Contractor's assessment is contractually correct; accept, reject or assess a quotation; issue or draft a contractual communication; determine the contractual effect of a clause; instruct or implement CE-018; claim legal or NEC4 compliance; provide legal advice.
Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018. When reused, name the relevant contractual role or accountable decision owner.

## Blank Register
CE018-SP-16
Corrective Action and Retest Register — blank
Reusable template. One row per action.
TEMPLATE — CONFIGURE BEFORE USE
Edit the white cells only. Every entry shown as [CONFIGURE] must be set by the accountable owner before this template is used on a live task.
Row marked EXAMPLE FORMAT shows the expected format of an entry. Delete that row before use — it is not data.
This blank sheet carries no CE-018 values. Do not copy worked-example values into it.
Name the retest scope when you raise the action
Deciding what to rerun after the fix is in invites the scope to shrink. Name the tests and controls at the point the action is raised.
A matter reserved to the accountable contractual role is marked reserved. It is not closed by assurance retest.
Action ID | Action | Accountable owner | Dependency | Due date | Date basis | Status | Retest scope on closure | Closure evidence | Retest outcome
[ID] | EXAMPLE FORMAT — [CONFIGURE] what must be done, stated as an action | [CONFIGURE named owner] | [EXC ID] | [CONFIGURE] | Assurance action target — not a contractual deadline | Open | [CONFIGURE] tests and controls rerun
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.

## Worked Example CE-018
CE018-SP-16
Corrective Action and Retest Register — CE-018 scenario S3 Rev 3.4
Eight actions. Six are assurance actions with named record owners; two are reserved to the Project Manager and are not closed by assurance retest.
COMPLETED CE-018 WORKED EXAMPLE — ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Fictional Demonstration Data. Every value is transcribed from the final issued CE-018 scenario record and is not rerun, rescored or reinterpreted here.
Source record: CE018_S3_NEC4_Decision_Readiness_Result_Rev3_4.json — actions
Read-only reference. Do not edit this sheet; copy the blank template instead.
Closure and retest columns are deliberately empty
At the 2026-03-31 evidence cut-off every action is open. Nothing had been closed and nothing had been retested, so recording anything in those columns would misstate the position.
A-07 and A-08 are reserved to the Project Manager. They appear in the action register for visibility, but their closure is a recorded determination, not an assurance retest.
Six assurance actions carry the date 2026-04-08 as an assurance action target. A-07 carries 2026-04-11, the configured contractual response date. The two kinds of date are labelled, never mixed.
Action ID | Action | Accountable owner | Dependency | Due date | Date basis | Status | Retest scope on closure | Closure evidence | Retest outcome
A-01 | Reconcile Forecast P07-X to Quotation Rev B line by line, or record a formal variance rationale for each CBS line. | Sofia Khan — Project Controls Lead | E-01 | 2026-04-08 | Assurance action target — not a contractual deadline | Open | T2, T3
A-02 | Reconcile the RISK-044-X position to the quotation and forecast, or record a formal rationale for the higher time and cost range. | Risk Manager | E-02 | 2026-04-08 | Assurance action target — not a contractual deadline | Open | T2, T3
A-03 | Apply CBS coding to RISK-044-X so its value links to a valid CBS account under XWALK-001. | Risk Manager | E-04 | 2026-04-08 | Assurance action target — not a contractual deadline | Open | T1, T2
A-04 | Register the CAL-5D-10H calendar definition, including any non-working days, and confirm whether the WSAE-M9000 variance is 10 or 12 working days. | Planning Manager | E-05 | 2026-04-08 | Assurance action target — not a contractual deadline | Open | T1, T2, T3
A-05 | Explain and evidence the WSAE-A1400 duration change from 7 to 9 days, and state whether it is attributed to CE-018. | Marcus Reed — Contractor Delivery Lead | E-06 | 2026-04-08 | Assurance action target — not a contractual deadline | Open | T2
A-06 | Supply the calculation build-up (rates, quantities, durations) behind the five Quotation Rev B amounts. | Marcus Reed — Contractor Delivery Lead | E-08 | 2026-04-08 | Assurance action target — not a contractual deadline | Open | T1, T2
A-07 | Determine whether the Contractor's assessment is incorrect for Clause 64.1 purposes, and whether the programme submitted satisfies Clause 62.2, and record both determinations. | Elena Brooks — NEC4 Project Manager | E-03 | 2026-04-11 | Configured contractual response date (RC-03, Clause 62.3 / 62.6) | Reserved to the Project Manager | Reserved — not closed by assurance retest
A-08 | Record the date and status of submission of UP13 for acceptance, and the acceptance or non-acceptance status, so control NEC-11 can be determined. | Elena Brooks — NEC4 Project Manager | E-07 | 2026-04-08 | Assurance action target — not a contractual deadline. No contractual programme-response date is calculable from the registered evidence. | Reserved to the Project Manager | Reserved — not closed by assurance retest
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.

## Retest Scope
CE018-SP-16
Retest scope by condition
What each of the four demonstrated conditions requires to be rerun. Transcribed from each condition's own issued record.
COMPLETED CE-018 WORKED EXAMPLE — ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED
Fictional Demonstration Data. Every value is transcribed from the final issued CE-018 scenario record and is not rerun, rescored or reinterpreted here.
Source record: the four final issued CE-018 scenario records
Read-only reference. Do not edit this sheet; copy the blank template instead.
Condition | Issued route | Actions raised | Retest requirement as issued | Retest source level
S1 Rev 3.0 | READY WITH CONDITIONS | 2 | T1: not required unless evidence is superseded. T2: not required unless a record is revised. T3: rerun T3 and the quotation-content and programme-alteration controls once the bounded exception is resolved, or at the configured response date, whichever is sooner. T4: not required. | Test level — stated for each test in the issued record
S2 Rev 3.1 | REWORK EVIDENCE PACK | 4 | T1; T2; T3; controls NEC-05, NEC-09, NEC-10 and NEC-11; Clause 64.1 triggers 2, 3 and 4; and the full cross-record reconciliation. | Test level — stated for each test in the issued record
S3 Rev 3.4 | STOP / RECONCILE | 8 | Close the reconciliation exceptions through the named actions with the record owners, then rerun T1, T2 and T3. T4 requires retest only if the requested action changes. Two exceptions are reserved to the Project Manager and are not closed by assurance retest. | Record level — no test-level retest field is issued, so the record-level statement is carried and labelled
S4 Rev 3.2 | REFER TO PROJECT MANAGER | 5 | Tests to rerun: T3 and T4. Controls to rerun: NEC-01, NEC-05, NEC-07, NEC-09, NEC-10 and NEC-12. | Record level — no test-level retest field is issued, so the record-level statement is carried and labelled
Where the retest statement sits in the source record matters
Two conditions state a retest requirement against each individual test. Two state it once at record level. Both are carried as issued, and the level is labelled.
The level is recorded rather than smoothed over because a record-level statement is less specific than a test-level one, and a reader is entitled to know which they are looking at.
No retest requirement is inferred, and none is borrowed from another condition.
Fictional Demonstration Data. Configured NEC4 process-assurance checks only — not a statement of NEC4 or legal compliance and not legal advice. Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018.