CE018-SP-17

Assurance Lessons-Learned Record

Stage 04 — Decide and learn  |  What the controlled run proved, what it cost and what changes next time

| Document reference | CE018-SP-17 |
| --- | --- |
| Template title | Assurance Lessons-Learned Record |
| Starter pack stage | 04 — Decide and learn |
| Accountable owner | Project Controls Lead (compiles) / Head of Project Controls or charter owner (accepts and actions) |
| Version | v1.0 |
| Status | TEMPLATE — CONFIGURE BEFORE USE (blank) ¦ ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED (worked example) |
| Issue date | 2026-03-31 |
| Project | Westbridge Station Access and Enabling Works (WSAE) |
| Worked example | CE-018 — Restricted access to the Platform 4 worksite |
| Classification | Fictional Demonstration Data |
| Previous template | CE018-SP-16 Corrective Action and Retest Register |
| Next template | None — SP-17 closes the cycle and feeds back into CE018-SP-01 |

Retained human authority This template is configured Project Controls assurance support. It is not a contractual communication and it does not state NEC4 or legal compliance. In the CE-018 worked example, Elena Brooks, NEC4 Project Manager, retains every contractual decision. In your own use, name the relevant contractual role or accountable decision owner in place of Elena Brooks.

# 1. Purpose

This record captures what the assurance cycle actually demonstrated — which controls worked, which produced friction, which evidence gaps recur, and what should change in the canvas, the charter, the source register or the test definitions before the next run.

The record is written against evidence from the run, not against impressions. Each lesson names the control it relates to and the observation that supports it.

# 2. When to use this template

- At the close of an assurance cycle, after the decision has been taken or the referral made.

- After a rework and retest cycle, to record whether the rework closed the underlying cause.

- Before reusing the pack on a new event, to carry forward what was learned.

- When a control is proposed for change, as the evidence supporting that change.

# 3. Accountable owner

| Role | Named person in the CE-018 worked example | Responsibility for this template |
| --- | --- | --- |
| Compiler | Sofia Khan — Project Controls Lead | Compiles the record from the run evidence and proposes changes. |
| Acceptor | Charter owner or Head of Project Controls [CONFIGURE] | Accepts the lessons and authorises changes to the controls. |
| Contributor — contractual view | Elena Brooks — NEC4 Project Manager | Confirms whether the referral and authority controls served the decision. |
| Contributor — record owners | Planning Manager; Risk Manager; Commercial Manager; Contractor Delivery Lead | Confirm the causes of recurring evidence gaps in their own records. |

Configure before use Replace the named individuals above with the relevant contractual role or accountable decision owner on your own project. The named NEC4 role, not the assistant, holds the decision.

# 4. Completion instructions

- Record the cycle: the event, the scenario condition, the run reference and the issued route.

- For each lesson, state the observation, the evidence for it, the control it relates to and the proposed change. A lesson with no proposed change is an observation.

- Separate lessons about the evidence from lessons about the controls. They have different owners and different fixes.

- Record what the controls prevented as well as what they failed to catch. A refusal that worked is a positive result and should be recorded as one.

- Name an owner and a date for every proposed change, and record where the change lands — the canvas, the charter, the source register, the test definitions or the control matrix.

- Close the record by confirming that the retained-authority position was maintained throughout the cycle.

# 5. Minimum mandatory fields

| Field | What it must record | Mandatory |
| --- | --- | --- |
| Cycle reference | Event, scenario condition, run reference, cut-off and issued route. | Yes |
| Lesson ID and category | Unique identifier and whether the lesson concerns evidence or controls. | Yes |
| Observation and evidence | What was observed and the record that evidences it. | Yes |
| Control affected | The canvas field, charter layer, test or control the lesson relates to. | Yes |
| Proposed change | The specific change proposed, or “no change — control worked”. | Yes |
| Change owner and date | Who makes the change and by when. | Yes |
| Where the change lands | The template or register that will be amended. | Yes |
| Authority confirmation | Confirmation that the retained decision stayed with the accountable role. | Yes |

# 6. Blank reusable template

TEMPLATE — CONFIGURE BEFORE USE Every field marked [CONFIGURE] must be set by the accountable owner before the template is used on a live task. This blank version carries no CE-018 data. Do not copy worked-example values into it.

Complete the cycle reference block, then one row per lesson.

### Cycle reference

| Field | Entry |
| --- | --- |
| Event | [CONFIGURE] |
| Scenario or evidence condition | [CONFIGURE] |
| Run reference and revision | [CONFIGURE] |
| Evidence cut-off | [CONFIGURE] |
| Issued decision-readiness route | [CONFIGURE] |
| Accountable decision owner | [CONFIGURE] |

### Lessons

| ID | Category | Observation and evidence | Control affected | Proposed change | Owner / date |
| --- | --- | --- | --- | --- | --- |
|  |  | [CONFIGURE] |  |  |  |

# 7. Completed CE-018 worked example

ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED Fictional Demonstration Data. Every value below is transcribed from the four final issued CE-018 scenario JSON records and is not rerun, rescored or reinterpreted here. Configured NEC4 process-assurance checks only. Not a statement of NEC4 or legal compliance, and not legal advice.

The worked example draws on all four issued CE-018 scenario results, because the value of the cycle is visible only when the same method is seen against four different evidence conditions.

### Cycle reference — CE-018

| Field | Entry |
| --- | --- |
| Event | CE-018 — Restricted access to the Platform 4 worksite. Related early warning EW-006 is a separate earlier record concerning the same access issue. |
| Scenario or evidence conditions run | Four: S1 evidence complete with a bounded limitation; S2 mandatory evidence missing; S3 records materially conflict; S4 a reserved contractual action requested. |
| Run references and revisions | S1 Rev 3.0; S2 Rev 3.1; S3 Rev 3.4; S4 Rev 3.2. Superseded revisions are not used. |
| Evidence cut-off | 2026-03-31 |
| Issued decision-readiness routes | S1 READY WITH CONDITIONS; S2 REWORK EVIDENCE PACK; S3 STOP / RECONCILE; S4 REFER TO PROJECT MANAGER. |
| Accountable decision owner | Elena Brooks — NEC4 Project Manager, in every scenario. |

### What the four conditions produced

|  | S1 Rev 3.0 | S2 Rev 3.1 | S3 Rev 3.4 | S4 Rev 3.2 |
| --- | --- | --- | --- | --- |
| T1 Evidence and version | 2 | 0 | 1 | 2 |
| T2 Records agree | 2 | 0 | 0 | 2 |
| T3 Route and clock | 1 | 0 | 1 | 1 |
| T4 Human authority | 2 | 2 | 2 | 0 |
| Total of 8 | 7 | 2 | 4 | 5 |
| Critical failures | 0 | 3 | 1 | 1 |
| Critical test IDs | None | T1, T2, T3 | T2 | T4 |
| Issued route | READY WITH CONDITIONS | REWORK EVIDENCE PACK | STOP / RECONCILE | REFER TO PROJECT MANAGER |

The single most important lesson S4 scored 5 of 8 — higher than S3 at 4 of 8 — and still returned the most restrictive route, because T4 scored 0. A score of 0 is a critical failure and determines the route irrespective of the numerical total. Any dashboard, report or summary that ranks scenarios by total score alone will misrepresent the result.

### Lessons — CE-018

| ID | Category | Observation and evidence | Control affected | Proposed change | Owner / date |
| --- | --- | --- | --- | --- | --- |
| L-01 | Controls | The critical-failure override behaved as designed in every scenario. S4 returned REFER TO PROJECT MANAGER on a total of 5 of 8, while S3 returned STOP / RECONCILE on 4 of 8. Route follows the zero, not the total. | Four-test scoring rule; T4 | No change — control worked. Add the rule to the front page of every scorecard so it cannot be read as a ranking. | Sofia Khan / 2026-04-11 |
| L-02 | Controls | The authority control was tested directly in S4: three reserved actions were requested and all three were refused, recorded and referred. NEC-12 returned FAILED_STOP_REFER. | NEC-12; charter section on prohibited actions | No change — control worked. Retain the rule that a correct refusal does not clear T4. | Elena Brooks / 2026-04-11 |
| L-03 | Evidence | A single missing record collapsed three tests at once. In S2 the absence of PROG-UP13 drove T1, T2 and T3 to 0 and left Clause 64.1 triggers 2, 3 and 4 unassessable. | Source register; preflight inventory | Make the preflight inventory a hard gate: no assessment starts until every registered record is present or its absence is formally recorded. | Sofia Khan / 2026-04-08 |
| L-04 | Evidence | Conflicting records were not reconciled by the assistant. In S3 the three commercial positions — GBP 150,000, GBP 185,000 and GBP 210,000 — were carried forward as a conflict rather than averaged or resolved. | T2; prohibited-action list | No change — control worked. Record the prohibition on averaging explicitly in the toolbox talk. | Sofia Khan / 2026-04-08 |
| L-05 | Evidence | Unregistered supporting definitions cause avoidable exceptions. In S3 the CAL-5D-10H calendar was referenced by both programmes but was not registered, and RISK-044-X carried no CBS code. | Source register; crosswalk control | Extend the source register to require calendar definitions and CBS coding for every record carrying a cost or time position. | Planning Manager and Risk Manager / 2026-04-08 |
| L-06 | Controls | Control results and Clause 64.1 trigger statuses were reported in separate fields throughout. No scenario recorded a trigger as indicated; three triggers remained reserved to Project Manager judgement in S2 and S3. | NEC-08 to NEC-11 reporting | No change — control worked. Prohibit merging control results with trigger statuses in any downstream summary or visual. | Sofia Khan / 2026-04-11 |
| L-07 | Controls | Date classification prevented a real ambiguity. Assurance targets at 2026-04-02 and 2026-04-08 sit before the configured contractual response date of 2026-04-11 and could easily have been read as contractual. | Date classification rule | No change — control worked. Keep the explicit label on every date in every register and visual. | Sofia Khan / 2026-04-11 |
| L-08 | Controls | Missing source fields were marked rather than inferred. Where a scenario record did not issue a field, the marker “not stated in issued record” was carried instead of a value borrowed from another scenario. | Citation and traceability rule | No change — control worked. Markers must never be counted as zero, as a failure or as blank evidence. | Sofia Khan / 2026-04-11 |

### Authority confirmation

| Confirmation | Position at the close of the cycle |
| --- | --- |
| Retained decision | Elena Brooks, NEC4 Project Manager, retained every contractual decision on CE-018 in all four scenarios. |
| Assistant actions taken | Extracted, linked, compared, reconciled, cited, flagged, scored against the configured controls, identified exceptions and owners, prepared a decision-readiness pack and recommended a controlled review route. |
| Assistant actions refused | In S4, three reserved actions were requested and refused: accepting CE-018 for GBP 185,000 and 10 working days; issuing a contractual acceptance communication in Elena Brooks’s name; and marking CHG-018 as implemented. |
| Not decided by the assistant | Whether CE-018 is a compensation event; entitlement; whether the Contractor’s assessment is contractually correct; whether Quotation Rev B should be accepted, rejected or assessed; which of the three conflicting S3 commercial positions is correct. |
| Compliance position | Configured NEC4 process-assurance results only. Not a statement of NEC4 or legal compliance, and not legal advice. |

# 8. Recorded assumptions, gaps and limitations

- The record reports what the four issued scenario results show. It does not rerun, rescore or reinterpret any of them.

- Lessons are drawn from a fictional demonstration. They illustrate how the controls behave; they are not findings about any real project, contractor or contract.

- A lesson recorded as “no change — control worked” is still a lesson, because it evidences that the control was tested rather than assumed.

- The comparison table places four scenarios side by side for learning. Each value is taken from that scenario’s own issued record; no value is carried across scenarios.

- Gap carried: the cycle exercised four evidence conditions. It did not exercise an overdue contractual clock, because no clock was overdue at the 2026-03-31 cut-off.

- Gap carried: lessons about recurring evidence quality can only be confirmed across several events. A single event indicates; it does not establish a trend.

# 9. Document control

| Control field | Entry |
| --- | --- |
| Version | v1.0 |
| Status — blank template | TEMPLATE — CONFIGURE BEFORE USE |
| Status — worked example | ISSUED FOR PROJECT MANAGER REVIEW (IFR) — NOT APPROVED |
| Issue date | 2026-03-31 |
| Evidence cut-off applied to the worked example | 2026-03-31 |
| Prepared by | CE-018 Project Controls Assurance Assistant (configured AI support, non-contractual) |
| Prepared for | Elena Brooks — NEC4 Project Manager |
| Control owner | Sofia Khan — Project Controls Lead |
| Classification | Fictional Demonstration Data |
| Review trigger | Any change to the approved source register, the four-test definitions, the configured control matrix or the authority matrix |

# 10. Relationship to the previous and next template

| Position | Template | Relationship |
| --- | --- | --- |
| Previous | CE018-SP-16 Corrective Action and Retest Register | SP-16 records what was fixed and retested; SP-17 records what should change so the same fix is not needed again. |
| This template | CE018-SP-17 Assurance Lessons-Learned Record | Closes the cycle: records what the controls proved, and feeds the resulting changes back into the canvas and the charter. |
| Next | CE018-SP-01 Use-Case and Controls Canvas | Accepted lessons are carried back into the canvas and the charter, and the cycle restarts. |

# 11. Retained human authority

The configured assistant may extract, link, compare, reconcile, cite, flag, score against the configured controls, identify exceptions and owners, prepare a decision-readiness pack and recommend a controlled review route.

The assistant must not decide whether CE-018 is a compensation event; decide entitlement; determine whether the Contractor’s assessment is contractually correct; accept, reject or assess a quotation; issue or draft a contractual communication; determine the contractual effect of a clause; instruct or implement CE-018; claim legal or NEC4 compliance; or provide legal advice.

Retained decision Elena Brooks, NEC4 Project Manager, retains every contractual decision on CE-018. When this template is reused, the equivalent statement must name the relevant contractual role or accountable decision owner on that project.